## Jan sites cancelled for 2012_DB
2012-12-01
Name | Vill | Block | Dist | Lon | Lat | Remark
Nischntopur p. School | Nischinto Pur | Bangaon | North-24-pgs | 23.0433 | 88.6926 | cancelled | Pipe line
Mehir Biswas | Kanak pur | Bangaon | North-24-pgs | 23.0415 | 88.7146 | cancelled | Pipe line
Swopon Biswas | Kanak pur | Bangaon | North-24-pgs | 23.041 | 88.7179 | cancelled | Pipe line
Panchayat | MajearGaram | Bangaon | North-24-pgs | 23.1111 | 88.6816 | cancelled | Pipe line
Gourihol school | MajearGaram | Bangaon | North-24-pgs | 23.1108 | 88.6857 | cancelled | Pipe line
Kali Bari | Baganpara | Ranaghat | Nadia | 23.1042 | 88.6786 | cancelled | Pipe line
Tufani Nuneya | Madhya Para | Ranaghat | Nadia | 23.1007 | 88.6792 | cancelled | Pipe line
Krisno Nuneya | Madhya Para | Ranaghat | Nadia | 23.0989 | 88.6787 | cancelled | Pipe line
Nepoti Das | Madhya Para | Ranaghat | Nadia | 23.0968 | 88.6802 | cancelled | Pipe line
Gopal Ray | Kanak pur | Bangaon | North-24-pgs | 23.0436 | 88.7144 | cancelled | Pipe line
Nemaye Das | Kanak pur | Bangaon | North-24-pgs | 23.0443 | 88.7126 | cancelled | Pipe line
Bappa Biswas | Kanak pur | Bangaon | North-24-pgs | 23.0457 | 88.706 | cancelled | Pipe line
Deaben Ray | Kanak pur | Bangaon | North-24-pgs | 23.0454 | 88.701 | cancelled | Pipe line
Shamol Biswas | Kanak pur | Bangaon | North-24-pgs | 23.043 | 88.7216 | cancelled | Pipe line
2012-12-01
mosalouddin dafara | Dharharkand | Swarupnagar | North-24-pgs | 22.85442/88.95529 |  | Pipe line | no sand | PWs 2011
ajijull par | Dharharkand | Swarupnagar | North-24-pgs | 22.8467 | 88.9525 | Pipe line | no sand | PWs 2011
eajarharuddin | Dharharkand | Swarupnagar | North-24-pgs | 22.8475 | /88.94735 | Pipe line | no sand | PWs 2011
bithri bollfild | Surupdha | Swarupnagar | North-24-pgs | 22.8473 | 88.933 | ok | Pure Sand | Cancal
Swrupnagar | 15/02/2012
Molongo Para | Malongo Para | Swarupnagar | North 24-pags | 22.828 | 88.8603 | Pipe line | no Sand | PWs 2011
Biswnath das | Malongo Para | Swarupnagar | North 24-pags | 22.8216 | 88.8547 | Pipe line | no sand | PWs 2011
Krisno Haldar | Malongo Para | Swarupnagar | North 24-pags | 22.8243 | 88.8552 | Pipe line | no sand | PWs 2011

## Feb 23_New sites for 2012_DB
sl no. | Date of pilot test | Name | Vill | Block | Dist | Lat | Long | Remark |  | Date
1 | 2012-02-24 | Monosatala | Addithya pur | Krishanganj | Nadia | 23.4217 | 88.7233 | Ok | 12ft-24- Sand | 23/02/2012
2 | 2012-02-24 | Sadhan Sadder | Addithya pur | Krishanganj | Nadia | 23.4185 | 88.7245 | Ok | 12ft-24- Sand
3 | 2012-02-24 | I C Dc School | Daspara | Krishanganj | Nadia | 23.4208 | 88.7276 | Cancal | no Sand

## detail info
SL_# | DW_ID | app id | project id | Type of Dugwell | SPONSORS | CONST YEAR | LATITUDE | LONGITUDE | DW_ID | construction status_Feb 2012 | OWNER | VILLAGE/PANCHAYET | BLOCK | DISTRICT | DW_ID | Name of the contact Person | Contact no. | uploaded on PWX | photo taken | demography yes/No
218 | PW218 | 362 | 483 | bore-dugwell | MSSCT/BPN | 2012 | 23.0433 | 88.6926 | PW218 | cancelled due to pipeline | Nischntopur primary School | Nischintopur | Bangaon | North-24-pgs | PW218 |  |  | uploaded
219 | PW219 | 362 | 484 | bore-dugwell | MSSCT/BPN | 2012 | 23.0415 | 88.7146 | PW219 | cancelled due to pipeline | Mihir Biswas | Kanakpur | Bangaon | North-24-pgs | PW219
220 | PW220 | 362 | 485 | bore-dugwell | MSSCT/BPN | 2012 | 23.041 | 88.7179 | PW220 | cancelled due to pipeline | Swapon Biswas | Kanakpur | Bangaon | North-24-pgs | PW220
221 | PW221 | 362 | 486 | bore-dugwell | MSSCT/BPN | 2012 | 23.1111 | 88.6816 | PW221 | cancelled due to pipeline | Panchayat | MajearGaram | Bangaon | North-24-pgs | PW221 |  |  | created
222 | PW222 | 362 | 487 | bore-dugwell | MSSCT/BPN | 2012 | 23.1108 | 88.6857 | PW222 | cancelled due to pipeline | Gourihol school | MajearGaram | Bangaon | North-24-pgs | PW222 |  |  | created
223 | PW223 | 362 | 488 | bore-dugwell | MSSCT/BPN | 2012 | 23.0436 | 88.7144 | PW223 | cancelled due to pipeline | Gopal Ray | Kanakpur | Bangaon | North-24-pgs | PW223 |  |  | created
224 | PW224 | 362 | 489 | bore-dugwell | MSSCT/BPN | 2012 | 23.0443 | 88.7126 | PW224 | cancelled due to pipeline | Nemaye Das | Kanakpur | Bangaon | North-24-pgs | PW224 |  |  | created
225 | PW225 | 362 | 490 | bore-dugwell | MSSCT/BPN | 2012 | 23.0457 | 88.706 | PW225 | cancelled due to pipeline | Bappa Biswas | Kanakpur | Bangaon | North-24-pgs | PW225 |  |  | created
226 | PW226 | 362 | 491 | bore-dugwell | MSSCT/BPN | 2012 | 23.0454 | 88.701 | PW226 | cancelled due to pipeline | Deben Ray | Kanakpur | Bangaon | North-24-pgs | PW226 |  |  | created
227 | PW227 | 362 | 492 | bore-dugwell | MSSCT/BPN | 2012 | 23.043 | 88.7216 | PW227 | cancelled due to pipeline | Shyamol Biswas | Kanakpur | Bangaon | North-24-pgs | PW227 |  |  | created
| MSSCT | app id | project id |  |  | PWSET6A |  |  | MSSCT | Construction status_Feb 2012
228 | PW228 |  |  | bore-dugwell | MSSCT/BPN | 2012 | 23.1042 | 88.6786 | PW228 | cancelled due to pipeline | Kali Bari | Baganpara | Ranaghat | Nadia | PW228
229 | PW229 |  |  | bore-dugwell | MSSCT/BPN | 2012 | 23.1007 | 88.6792 | PW229 | cancelled due to pipeline | Tufani Nuneya | Madhya Para | Ranaghat | Nadia | PW229
230 | PW230 |  |  | bore-dugwell | MSSCT/BPN | 2012 | 23.0989 | 88.6787 | PW230 | cancelled due to pipeline | Krisno Nuneya | Madhya Para | Ranaghat | Nadia | PW230
231 | PW231 |  |  | bore-dugwell | MSSCT/BPN | 2012 | 23.0968 | 88.6802 | PW231 | cancelled due to pipeline | Nepoti Das | Madhya Para | Ranaghat | Nadia | PW231
232 | PW232 |  |  | bore-dugwell | MSSCT/BPN | 2012 |  |  | PW232 | [5 empty] | PW232
233 | PW233 |  |  | bore-dugwell | MSSCT/BPN | 2012 |  |  | PW233 | [5 empty] | PW233
234 | PW234 |  |  | bore-dugwell | MSSCT/BPN | 2012 |  |  | PW234 | [5 empty] | PW234
235 | PW235 |  |  | bore-dugwell | MSSCT/BPN | 2012 |  |  | PW235 | [5 empty] | PW235
236 | PW236 |  |  | bore-dugwell | MSSCT/BPN | 2012 |  |  | PW236 | [5 empty] | PW236
237 | PW237 |  |  | bore-dugwell | MSSCT/BPN | 2012 |  |  | PW237 | [5 empty] | PW237
| MSSCT | app id | project id |  |  | PWSET6B |  |  | MSSCT | Construction status_Feb 2012 |  |  |  |  | various donors