## Expenses Details_PWX_Palmyra
Palmyra NGO - Auroville - Sanitation Activity through Rural Women SHG, Endiyur Village
Actual Expenditure from April to November 2012
Funded by Peer Water Exchange, Bangalore
(in Rs.)
| Detailed Expenditure | PWX Fund Received | Expenditure | Balance
A | Staff Expenses - Salary Cost | 105000 | 70000 | 35000
B | Program Costs - Training and Activities | 44500 | 29500 | 15000
C | Program Cost (construction of 25 toilets) | 337500 | 340184 | -2684
D | Transportation | 24000 | 22226 | 1774
E | Local Administration (staff welfare, stationary, communication, etc.) | 36000 | 32285 | 3715
F | Monitoring, Liason and Net working (Accounts / Documentation) | 15000 | 12564 | 2436
G | Administrative Fee of Palmyra 5% | 39350 | 26233 | 13117
| Total | 601350 | 532992 | 68358
| Cash in Bank |  |  | 36816
| Cash in Hand |  |  | 31542
| Beneficiary Contribution |  |  | 609760
| Subsidy received from BDO for 10 toilets |  |  | 30470 | 69000 | 99470
Total Funds Mobilized for 25 Toilets Construction
| Physical Work | Actual Amount in Rs. | % | As per Proposal | Increased Investment
| Beneficiary Contribution | 609760 | 58.1046 | 335000 | 274760
| PWX Grant | 340187 | 32.4168 | 337500 | 2687
| Subsidy from BDO | 99470 | 9.4786 | 80000 | 19470
| Total | 1049417 | 100 | 752500 | 296917
|  |  |  | Percentage | 39.4574
Beneficiaries invested 40% additional amount for construction of toilet and bathroom. It replies that the people participation as well as the Government Subsidy has been considerably increased and able to mobilize the fund for their needs. Palmyra has implemented the project in a successful manner in the village. We thank to PWX, People in the Village , Village Panchayath Council and the Block Development Officers to complete the project in a succesfull manner.
Note on G21: user: Yet to receive. Increased subsidy from 3200 to 4600 per toilet.