## Sheet1
TANZANIA MISSION TO THE POOR AND DISABLED (PADI)
P.o.Box 517, Songea-Ruvuma, Tanzania, East Africa, Land line: 0252600958, Mobile 0754 653942/0787376693,
padijune1999@yahoo.com and E-mail: padi_msigwa@yahoo.com
LONDONI SECONDARY SCHOOL-BORE HOLE CONSTRUCTION-FINANCIAL REPORT JANUARY -APRIL 2010
DURATION: 4 Months
IMPLEMENTING ORGANISATION: TANZANIA MISSION TO THE POOR AND DISABLED (PADI)
AMOUNT RECEIVED: Tsh 8,441,921.42/= ($6426.94)
AMOUNT USED: Tsh 8,406,000/= ($6400)
MONEY TRANSFER & DRAFT COST: Tsh 42,209.60/= ($32.13)
REMAIN BALANCE: Tsh 35,921.42/= ($27.34)
EXCHANGE RATE: 1313.52
SN | ITEM | REFERENCE: | AMOUNT USED IN Tsh. | TOTAL IN Tsh. | TOTAL IN USD
-Receipt no. (Rec)
-Petty Cash no. (PC)
1. | Drill Production well | Rec. No. 032 | 2400000
| Transportation of Pump set | Rec. No. 032 | 300000
| Install pump set and construct slab | Rec. No. 032 | 300000 | 3000000 | 2283.9393
| Conduct water well analysis | Rec No. 033 | 100000
| Supply SWN 80 Pump set | Rec No. 033 | 2200000 | 2300000 | 1751.0202
| Supply 10 PVC (B) CASING 7 plain | Rec No. 036 | 1300000
| Develop Borehole for a minimum yield of 800lt/hr | Rec No. 036 | 250000
| Conduct water quality analysis | Rec No. 036 | 50000 | 1600000 | 1218.101
| Prepare completion report | payroll 1 | 30000 | 30000 | 22.8394
2 | Project Monitoring | PCV NO. 1,2,3,4 | 400000 | 400000 | 304.5252
| SUB TOTAL |  | 7330000 | 7330000 | 5580.4251
3 | Administration cost
| -Digital Camera | Rec No 35582 | 450000
| -Printer office jet & Flash disk | Rec No.8218 | 280000
| -Project Coordinator Allowance | PCV No 5 | 100000
| -Finance Officer Allowance | PCV No. 6 | 60000
| Video shooting cost | Rec No.00560 | 140000
| Fuel & motorbike repair | Rec No.02779,03313 | 46000
| SUB TOTAL |  | 1076000 | 1076000 | 819.1729
| GRAND TOTAL |  | 8406000 | 8406000 | 6399.598