## PWX
Aqua Clara International |  |  | Aqua Clara International
Proposed Budget for implementation of training center and water filtration training program expansion in the Kisii region, including the launch of 10 new filter-constructing groups. |  |  | Actual budget after implementation
Kenya |  |  | Kenya
Item | Description | Estimated Cost | Category Name | Actual 2010 Expenses | Actual 2011 Expenses | Total Project Expenses | Amount Over/Under Budget | Notes on actual
Building Remodel as example and training center (H2Ope Center) | Remodel donated building into office space for continual training and tracking of Kisii-area AC water programmes (H2Ope Center renovation). One classroom for 20+ participants, one conference room, and two offices for recordkeeping and laboratory (water testing) work. | 5000 | PWX Remodel | 7832.1775 | 4948.53 | 12780.7075 | 7780.7075 | We went significantly over budget here, as our original budget was to rehab a more finished office space, which was to be donated, but didn't go through due to local politics, forcing us to go with an option that required more work.
Latrine Construction @ H20pe Center | The donated building's latrines (3) are in complete disrepair. Renovate them as an example of proper latrine construction, including an example of a urine diverting composting toilet, complete with a small sample garden plot, all constructed in collaboration with visiting Michigan State Professor while providing training for local personnel. | 2000 | PWX Sanitation | 2840.225 | 0 | 2840.225 | 840.225 | Over budget due to construction difficulties as well as larger than anticipated costs in constructing agricultural demonstration plots for eco-san fertilizer demonstration.
Rainwater Harvesting Construction @ H2Ope Center | Construction of three sample rainwater harvesting catchments (small scale rooftop - 5,000 liters and under), each with different size plastic containers and bodies for use at the training center as well as for training examples for the local communities and personnel. | 1200 | PWX Rainwater | 1314.775 | 0 | 1314.775 | 114.775 | Slightly over budget, as we added 12,250 liters of water storage, using larger tanks than budgeted for to provide sufficient water for our agricultural demonstration.
Oxfam DelAgua Dual Incubator Portable Laboratory | Purchase of water testing equipment to be permanently used in Kisii region for the ongoing testing of water sources and for quality control of constructed filters. | 3100 | PWX Incubator | 0 | 0 | 0 | -3100 | We had a Wagtech kit loaned long-term through the Ministry of Sanitation and Health, so we are able to utilize that in conducting our water test.
Consumables for 600 water tests with Oxfam kit | Filters will be tested by local staff on a randomized basis during the first year of operation. | 360 | PWX Laboratory Supplies | 505.45 | 568.76 | 1074.21 | 714.21 | We have run more tests than anticipated, due to two partnership studies with area universities.
Hach Turbidimeter | Easy to use portable turbidimeter for continual testing of water filters. | 930 | PWX Turbidimeter | 805.79 | 0 | 805.79 | -124.21 | We purchased a cheaper version of this turbidimeter.
Local Coordinator (part-time) | Will network and organize all training and oversight activities with area schools and C.D.O.s, etc. and who will also be involved in all training activities; 12 months. | 1560 | PWX Coordinator Wages | 250 | 3269.11 | 3519.11 | 1959.11 | We hired a full-time coordinator to help manage our expansion.
Local program manager (full-time) | Fully involved in communicating, tracking, testing and organizing to ensure proper follow-up (continual training and support for CDOs, as well as tracking and testing for quality control, etc.); 12 months. | 3840 | PWX Manager Wages | 1569.25 | 3285.22 | 4854.47 | 1014.47
Train and Tool 10 new Community Development Officers in launching and running their filter construction enterprises | Train 10 new C.D.O.s in water filter construction as well as related WASH practices; supply all necessary tools for the construction of filters as well as materials for filter promotion and documents for tracking. | 1000 | PWX Training | 0 | 2359.1753 | 2359.1753 | 1359.1753 | Slightly over budget, as we moved to a residential five day training from a three day commuter training.
Provide supplies to 10 newly trained CDO's sufficient for their first 50 filters and first 50 safe water storage containers | All producers are initially supplied with materials sufficient for their first 50 sales. They are selling these units - both filters and tapped water storage and distribution containers - and thereby pay back into a bank account which is available to reorder another load of materials when needed. | 6500 | Supply | 0 | 3789.4659 | 3789.4659 | -2710.5341 | As we were over on other elements, we began our new trainees with a supply of 25, rather than 50, units.
10 (part time) Community Health Workers | 10 community health workers have been trained, and will be tasked with meeting with each new filter purchaser as they are sold. This ensures more effective training of the end-user through repetition of training on filter use, while also bringing training on a variety of related health, hygiene and sanitation practices to each purchasing household, as well as to the schools where the filters are built. | 3000 | CHW Wages | 599.625 | 1960.1682 | 2559.7932 | -440.2068 | We assigned fewer household visits than anticipated.
Total |  | 28490 | Actual Project Expenses Total | 15717.2925 | 20180.4294 | 35897.7219 | 7407.7219 | The extra program costs were contributed from other sources.
Deliverables
Item | Description | Direct # from PWX Funds | Overall 1-year Number | Notes
Training Center & Office | ACI bases its local staff, training, tracking and testing out of local offices. Our main office was the renovation of space donated by the community and government of Rigoma. | 1 | 1.5 | ACI also opened up a new satellite office in Eldoret during 2011, while it's main training and tracking center remains in Rigoma (Kisii region), which was funded by PWX funds.
9 new CDEs building filters | CDE's (formerly CDOs) are community members trained in building, marketing, installing and servicing biosand water filters and safe water storage containers. | 9 | 17 | ACI trained 17 new Filter Entrepreneurs (now known locally as 'Community Development Entrepreneurs') during 2011, 9 funded by PWX. 13 of these were in the new Eldoret region, and the other 4 in Kisii.
Water Filters Installed in Schools | ACI biosand filters installed and used by schools. They are checked on twice per month by ACI Community Health Promoters. | 18 | 34
Students Benefiting from ACI programs at schools | ACI installs filters at schools, and also run water and hygiene clubs at our partner schools. Our school size varies widely, but averages around 500 students. | 5024 | 9024
Water Filters Installed in Households | Once filters are demonstrated at schools, CDEs begin selling them to their community members. | 282 | 796
Safe Water Storage Installed in Schools | ACI SWS containers installed and used by schools. They are checked on twice per month by ACI Community Health Promoters. | 18 | 34
Safe Water Storage Installed in Households | Once SWS containers are demonstrated at schools, CDEs begin selling them to their community members. | 220 | 692
Handwashing Stations Installed in Schools | ACI handwashing stations installed and used by schools. They are checked on twice per month by ACI Community Health Promoters. | 18 | 34
Direct beneficiaries (non-school) | Our average household served is 5.8 persons, so we estimate a total number served by 5.8* household units installed. | 1635.6 | 4616.8
Community Health Promoters | ACI-trained CHPs visit schools and households, providing training to students and families in safe water and hygiene, while also inspecting filter use and performance. | 10 | 17
Household Health Promotion Visits / Trainings | ACI-trained community health promoters visit each household with ACI products installed, checking on product use and function while also training in safe water and hygiene practices. | 282 | 796
School Water and Hygiene Clubs Formed and Supported | ACI-trained CHPs run school water and hygiene clubs while also ensuring proper school use of ACI installed products. | 9 | 17