## SCHOOLS 2012-13
PEACE CORPS HEALTHY SCHOOLS 2013-14 , GUATEMALA
PC Currently Working With School | NUMBER | School, Village, and Town | PROPOSED PROJECT | NEED SECURITY DOORS---YES | NUMBER OF STUDENTS | WATER SOURCE | PRESENT CONDITION | $-COST OF HAND WASHING STATION | $-EXTRAS- RAIN STORAGE TANK; OTHER TANKS;AND PUMPS | NOTES ON EXTRAS AND OTHER COMMENTS | TOTAL COST IN DOLLARS | $- VILLAGE CONTRIBUTION--SEE "NOTES" TAB | NORTH | WEST
YES | 1 | CHUIMACABAL, ZUNIL, XELA | Wall-style 8 faucets-TRAPIADOR | NO | 106 | SUFFICIENT | 1- faucets, 106 students | 1706.6452 | 0 | NONE | 1706.6452 | 232 | 14.7835 N | 91.4832 W
YES | 2 | FRAY BARTOLO, Zunil | 8 CHORROS Y 4 CHORROS CON TRAPIADORS | NO | 500 | SUFFICIENT | 6 faucets | 1706.6452 | 1561.6129 | PROJECT INCLUDES AN 8 AND A 4 FAUCET HAND WASHING STATION | 3268.2581 | 696 | 14° 47' 5.7 " | 91° 28' 57.7 "
YES | 3 | CHOTZAQUE, SAN BARTOLO | 4 FAUCET HAND WASHING STATION | NO | 110 | SUFFICIENT | 1 faucets, 110 students | 1664.8387 | 0 | 4 FAUCET HAND WASHING STATION | 1664.8387 | 232 | 15 05´ 24.4¨ | 91 27´ 53.0"
YES | 4 | PACHUCHU,SAN BARTOLO | SCHOOL WATER SYSTEM REPAIRS | NO | 141 | SUFFICIENT | 1 faucets, 141 students | 0 | 1500 | REPAIRS TO EXISTING WATER SYSTEM AND FAUCETS. | 1500 | 543 | 15 05´ 56.3" | 91 28´ 38.7"
YES | 5 | XETALBIJOJ, CAJOLA, XELA | Wall-style 8 faucets | YES | 376 | SUFFICIENT | 1 faucets, 376 students | 1706.6452 | 1500 | REPAIR PUMP INSTALLATION | 3206.6452 | 696 | 14°55'42.51"N | 91°36'1.99"W
YES | 6 | MONZON MALICE, CAJOLA , XELA | 1 --8 FAUCET WALL HAND WASHING STATIONS AND 2--4 FAUCET | YES | 692 | SUFFICIENT | 3- faucets, 692 students | 1965.3548 | 3000 | 1 --8 FAUCET WALL HAND WASHING STATIONS AND 2--4 FAUCET - WITH SEEPAGE PITS FOR HAND WASHING STATIONS | 4965.3548 | 696 | 14°53'27.09"N | 91°36'2.30"W
YES | 7 | LOS DIAZ , CAJOLA, XELA | 2 --4 FAUCET HAND WASHING STATIONS | YES | 232 | SUFFICIENT | 5- faucets, 232students | 1561.6129 | 1561.6129 | 2 --4 FAUCET HAND WASHING STATIONS | 3123.2258 | 311 | 14°55'41.02"N | 91°37'20.35"W
YES | 8 | CAJOLA CHIQUITO,CAJOLA, XELA | TWO --8 FAUCET WALL HAND WASHING STATION | YES | 396 | VILLAGE WATER TWICE A WEEK | 3 -faucets, 396 students | 3930.7097 | 0 | NONE | 3930.7097 | 464 | 14°55'59.65"N | 91°36'8.87"W
YES | 9 | LA CANOA,PATZICIA | PUMP RENOVATIONS | NO | 292 | SUFFICIENT with well | 5 FAUCETS FOR 150 STUDENTS | 1108.6452 | 500 | SEEPAGE PIT FOR PILA AND WELDING TO REPLACE BATHROOM DOORS;AND REPAIRS TO PUMP SYSTEM | 1608.6452 | 232 | 14°40'16.02"N | 90°58'10.07"W
YES | 10 | EL CAIMAN #3,PATZICIA | 3 BATHROOMS and septic tank | NO | 252 | Village water system and school pump | 3 latrines and new hand washing station | 0 | 6257.4194 | Build a septic tank with 3 new bathrooms and convert the 3 latrines to flush toilets | 6257.4194 | 696 | 14°41'0.47"N | 90°57'17.85"W
YES | 11 | EL POTRERILLO,PATZICIA, CHIMAL | Wall-style 4 faucets | YES | 20 | SUFFICIENT | 1-faucets, 20 students | 1706.6452 | 0 | NONE | 1706.6452 | 232 | 14°39'40.76"N | 90°58'14.03"W
YES | 12 | PACHIMULIN, PATZUN, CHIMAL | 12 CHORROS-WELL HEAD-TUBING-PUMP-1100 TANK | NO | 184 | PERIODIC | 2-faucets, 184 students | 2948.0323 | 1500 | Project will include a 12 faucet hand washuing station; 1100 liter storage tank; and well improvements | 4448.0323 | 361 | 14.6151N | 90.9721W
YES | 13 | LAS CAMILIAS,PATZUN | 10000 LITER RAIN STORAGE TANK-GUTTERS | NO | 250 | None--children carry water |  | 0 | 4781.0116 | 10000 LITER TANK-GUTTERS | 4781.0116 | 696 | 14.6151N | 90.9721W
YES | 14 | 29 DICEMBER, ZARAGOZA | 6 faucet wall style | YES | 48 | SUFFICIENT | 1 FAUCET FOR 48 STUDENTS | 1965.3548 | 0 | NONE | 1965.3548 | 232 | 14° 30’ 28”N | 90° 52’ 30”W
YES | 15 | PUERTA ABAJO, ZARAGOZA, CHIMAL | Wall-style 8 faucets | YES | 139 | SUFFICIENT | 4-faucets, 139 students | 1965.3548 | 0 | NONE | 1965.3548 | 232 | NA | NA
|  |  |  | DONATION PER STUDENT-$ | TOTAL STUDENTS |  |  | 23936.4839 | 22161.6568 |  | 46098.1406 | 6551
|  |  |  | 12.3323 | 3738 |  |  | TOTAL COSTS | 46098.1406 |  |  | CONTRIBUTION FROM COMMUNITY
NOTE: FIGURES REPRESENTED IN THE SUMMATION ARE BEST ESTIMATES DUE TO THE DIVERSE NATURE OF SOME PROJECTS AND THE DIFFERENT GEOGRAPHIC AREA OF THE SCHOOLS. Some projects have multiple structures and therefore we have averaged the supervision and sustainability review amounts in the summation.

## WALL STYLE-8
AGUA PARA LA SALUD
2012-2013
Hand washing station 8 faucets with seepage pit and security doors | TOTAL QUANTITY | PRICE PER UNIT | US $ | 1965.3548
|  |  | Quetzales | 15231.5
| TOTAL |  | TOTAL PRICE | DESCRIPTION
| CANTID. | PRECIO |  | DESCRIPCION
2 | 2 | 225 | 450 | RIVER SAND ( M^3)
2 | 2 | 200 | 400 | GRAVEL( M^3)
20 | 20 | 74 | 1480 | CEMENTO |  |  | 2550
6 | 6 |  | 0 | ROCK FOR BALAST(M^3) community
1 | 1 | 300 | 300 | WOOD 8 FEET --2" X 4" (DOZEN)
1.5 | 1.5 | 300 | 450 | WOOD BOARDS 8 FEET(DOZEN)
1.5 | 1.5 | 1200 | 1800 | SKILLED LABOR 1 (SEMANA)
1 | 1 | 750 | 750 | ACCOUNTING , DOCUMENTATION, DESIGN
1 | 1 | 1000 | 1000 | SUBSISTANCE
1 | 1 | 1400 | 1400 | SUPERVISION
1 | 1 | 2000 | 2000 | FREIGHT-GAS - COMMUNICATION
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
|  | SUB-TOTAL | 11630
MISC.
5 | 5 | 7 | 35 | TIE WIRE
1 | 1 | 300 | 300 | IRON RE-BAR 3/8" (POR QUINTAL)
2 | 2 | 7 | 14 | NAILS 2 1/2" (POR LIBRA)
2 | 2 | 7 | 14 | NAILS 4" (POR LIBRA)
1 | 1 | 10 | 10 | HACK SAW BLADE
5 | 5 | 2.5 | 12.5 | ROLLS OF TEFLON
4 | 4 | 20 | 80 | MASONS BUCKETS
2 | 2 | 800 | 1600 | SECURITY DOORS
|  | SUB-TOTAL | 2065.5
HG
4 | 4 | 3 | 12 | ELBOW HG 90° 1/2"
9 | 9 | 5 | 45 | COUPLING HG 1/2"
8 | 8 | 52 | 416 | FAUCETS 1/2" ( NIBICO O PP)
1 | 1 | 20 | 20 | VALVE 1/2" PVC
1 | 1 | 135 | 135 | TUBE HG 1/2" (POR NIPLES)
7 | 7 | 10 | 70 | TEE HG 1/2"
4 | 4 | 22 | 88 | DRAIN COVER 2" PVC
|  | SUB-TOTAL | 786
PVC
2 | 2 | 3 | 6 | MALE ADAPTOR 1/2"
2 | 2 | 22 | 44 | CLEAN OUT CAP 2" CON ROSCA, MACHO | Wall style hand washing station with security doors
2 | 2 | 15 | 30 | FEMALE ADAPTOR 2"
1 | 1 | 30 | 30 | TUBO 1/2" 315PSI
2 | 2 | 15 | 30 | ELBOW 90° DRENAJE 3"
1 | 1 | 45 | 45 | PVC CROSS DRENAJE 2"
4 | 4 | 20 | 80 | TEE DRENAJE 2"
3 | 3 | 120 | 360 | DRAINAGE TUBE 2"
1 | 1 | 25 | 25 | SCREEN/CEDASO POR METRO
1 | 1 | 100 | 100 | PVC GLUE 1/32 GAL.
|  | SUB-TOTAL | 750
|  | TOTAL | 15231.5
Hand washing station 8 faucets without security doors | TOTAL QUANTITY | PRICE PER UNIT | US $ | 1706.6452
|  |  | Quetzales | 13226.5
| TOTAL |  | TOTAL PRICE | DESCRIPTION
| CANTID. | PRECIO |  | DESCRIPCION
3 | 3 | 225 | 675 | RIVER SAND ( M^3) | E2 times 2 | 3930.7097
3 | 3 | 200 | 600 | GRAVEL( M^3) | E2 times 3 | 5896.0645
20 | 20 | 74 | 1480 | CEMENTO | E2 times 1.25 | 2456.6935
6 | 6 |  | 0 | ROCK FOR BALAST(M^3) community | E2 times 1.5 | 2948.0323
1 | 1 | 300 | 300 | WOOD 8 FEET --2" X 4" (DOZEN)
1.5 | 1.5 | 300 | 450 | WOOD BOARDS 8 FEET(DOZEN)
1.4 | 1.4 | 1200 | 1680 | SKILLED LABOR 1 (SEMANA)
1 | 1 | 750 | 750 | TRAINEE
1 | 1 | 750 | 750 | SUBSISTANCE
1 | 1 | 1400 | 1400 | SUPERVISION
1 | 1 | 1500 | 1500 | FREIGHT-GAS - COMMUNICATION
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
|  | SUB-TOTAL | 11185
MISC.
5 | 5 | 7 | 35 | TIE WIRE
1 | 1 | 300 | 300 | IRON RE-BAR 3/8" (POR QUINTAL)
2 | 2 | 7 | 14 | NAILS 2 1/2" (POR LIBRA)
2 | 2 | 7 | 14 | NAILS 4" (POR LIBRA)
1 | 1 | 10 | 10 | HACK SAW BLADE
5 | 5 | 2.5 | 12.5 | ROLLS OF TEFLON
4 | 4 | 20 | 80 | MASONS BUCKETS
0 | 0 | 800 | 0 | SECURITY DOORS
|  | SUB-TOTAL | 465.5
HG
4 | 4 | 3 | 12 | ELBOW HG 90° 1/2"
9 | 9 | 5 | 45 | COUPLING HG 1/2"
8 | 8 | 52 | 416 | FAUCETS 1/2" ( NIBICO O PP)
1 | 1 | 20 | 20 | VALVE 1/2" PVC
9 | 9 |  | 0 | NIPLE HG 1/2" 10 CM
1 | 1 | 135 | 135 | TUBE HG 1/2" (POR NIPLES)
7 | 7 | 10 | 70 | TEE HG 1/2"
4 | 4 | 22 | 88 | DRAIN COVER 2" PVC
|  | SUB-TOTAL | 786
PVC
2 | 2 | 3 | 6 | MALE ADAPTOR 1/2"
2 | 2 | 22 | 44 | CLEAN OUT CAP 2" CON ROSCA, MACHO
2 | 2 | 15 | 30 | FEMALE ADAPTOR 2"
1 | 1 | 30 | 30 | TUBO 1/2" 315PSI
2 | 2 | 15 | 30 | ELBOW 90° DRENAJE 3"
1 | 1 | 45 | 45 | PVC CROSS DRENAJE 2"
6 | 6 | 20 | 120 | TEE DRENAJE 2"
3 | 3 | 120 | 360 | DRAINAGE TUBE 2"
1 | 1 | 25 | 25 | SCREEN/CEDASO POR METRO
1 | 1 | 100 | 100 | PVC GLUE 1/32 GAL.
|  | SUB-TOTAL | 790
|  | TOTAL | 13226.5

## WALL STYLE-4
AGUA PARA LA SALUD |  |  |  |  | AGUA PARA LA SALUD
|  | 2012-2013 |  |  |  |  | 2012-2013
Hand washing station 4 faucets with seepage pit and security doors | TOTAL QUANTITY | PRICE PER UNIT | US $ | 1664.8387 | Hand washing station 4 faucets with seepage pit | TOTAL QUANTITY | PRICE PER UNIT | US $ | 1561.6129
|  |  | Quetzales | 12902.5 |  |  |  | Quetzales | 12102.5
| TOTAL |  | TOTAL PRICE | DESCRIPTION |  | TOTAL |  | TOTAL PRICE | DESCRIPTION
| CANTID. | PRECIO |  | DESCRIPCION |  | CANTID. | PRECIO |  | DESCRIPCION
2 | 2 | 225 | 450 | RIVER SAND ( M^3) | 2 | 2 | 225 | 450 | RIVER SAND ( M^3)
2 | 2 | 200 | 400 | GRAVEL( M^3) | 2 | 2 | 200 | 400 | GRAVEL( M^3)
14 | 14 | 74 | 1036 | CEMENTO | 14 | 14 | 74 | 1036 | CEMENTO
6 | 6 |  | 0 | ROCK FOR BALAST(M^3) community | 6 | 6 |  | 0 | ROCK FOR BALAST(M^3) community
1 | 1 | 300 | 300 | WOOD 8 FEET --2" X 4" (DOZEN) | 1 | 1 | 300 | 300 | WOOD 8 FEET --2" X 4" (DOZEN)
1.5 | 1.5 | 300 | 450 | WOOD BOARDS 8 FEET(DOZEN) | 1.5 | 1.5 | 300 | 450 | WOOD BOARDS 8 FEET(DOZEN)
1 | 1 | 1200 | 1200 | SKILLED LABOR 1 (SEMANA) | 1 | 1 | 1200 | 1200 | SKILLED LABOR 1 (SEMANA)
1 | 1 | 750 | 750 | ACCOUNTING , DOCUMENTATION, DESIGN | 1 | 1 | 750 | 750 | ACCOUNTING , DOCUMENTATION, DESIGN
1 | 1 | 700 | 700 | SUBSISTANCE | 1 | 1 | 700 | 700 | SUBSISTANCE
1 | 1 | 1500 | 1500 | SUPERVISION | 1 | 1 | 1500 | 1500 | SUPERVISION
1 | 1 | 2000 | 2000 | FREIGHT-GAS - COMMUNICATION | 1 | 1 | 2000 | 2000 | FREIGHT-GAS - COMMUNICATION
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE | 1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
|  | SUB-TOTAL | 10386 |  |  |  | SUB-TOTAL | 10386
|  |  |  | MISC. |  |  |  |  | MISC.
5 | 5 | 7 | 35 | TIE WIRE | 5 | 5 | 7 | 35 | TIE WIRE
1 | 1 | 300 | 300 | IRON RE-BAR 3/8" (POR QUINTAL) | 1 | 1 | 300 | 300 | IRON RE-BAR 3/8" (POR QUINTAL)
2 | 2 | 7 | 14 | NAILS 2 1/2" (POR LIBRA) | 2 | 2 | 7 | 14 | NAILS 2 1/2" (POR LIBRA)
2 | 2 | 7 | 14 | NAILS 4" (POR LIBRA) | 2 | 2 | 7 | 14 | NAILS 4" (POR LIBRA)
1 | 1 | 10 | 10 | HACK SAW BLADE | 1 | 1 | 10 | 10 | HACK SAW BLADE
5 | 5 | 2.5 | 12.5 | ROLLS OF TEFLON | 5 | 5 | 2.5 | 12.5 | ROLLS OF TEFLON
4 | 4 | 20 | 80 | MASONS BUCKETS | 4 | 4 | 20 | 80 | MASONS BUCKETS
1 | 1 | 800 | 800 | SECURITY DOORS | 0 | 0 | 800 | 0 | SECURITY DOORS
|  | SUB-TOTAL | 1265.5 |  |  |  | SUB-TOTAL | 465.5
|  |  |  | HG |  |  |  |  | HG
4 | 4 | 3 | 12 | ELBOW HG 90° 1/2" | 4 | 4 | 3 | 12 | ELBOW HG 90° 1/2"
6 | 6 | 5 | 30 | COUPLING HG 1/2" | 6 | 6 | 5 | 30 | COUPLING HG 1/2"
4 | 4 | 52 | 208 | FAUCETS 1/2" ( NIBICO O PP) | 4 | 4 | 52 | 208 | FAUCETS 1/2" ( NIBICO O PP)
1 | 1 | 20 | 20 | VALVE 1/2" PVC | 1 | 1 | 20 | 20 | VALVE 1/2" PVC
1 | 1 | 135 | 135 | TUBE HG 1/2" (POR NIPLES) | 1 | 1 | 135 | 135 | TUBE HG 1/2" (POR NIPLES)
3 | 3 | 10 | 30 | TEE HG 1/2" | 3 | 3 | 10 | 30 | TEE HG 1/2"
3 | 3 | 22 | 66 | DRAIN COVER 2" PVC | 3 | 3 | 22 | 66 | DRAIN COVER 2" PVC
|  | SUB-TOTAL | 501 |  |  |  | SUB-TOTAL | 501
|  |  |  | PVC |  |  |  |  | PVC
2 | 2 | 3 | 6 | MALE ADAPTOR 1/2" | 2 | 2 | 3 | 6 | MALE ADAPTOR 1/2"
2 | 2 | 22 | 44 | CLEAN OUT CAP 2" CON ROSCA, MACHO | 2 | 2 | 22 | 44 | CLEAN OUT CAP 2" CON ROSCA, MACHO
2 | 2 | 15 | 30 | FEMALE ADAPTOR 2" | 2 | 2 | 15 | 30 | FEMALE ADAPTOR 2"
1 | 1 | 30 | 30 | TUBO 1/2" 315PSI | 1 | 1 | 30 | 30 | TUBO 1/2" 315PSI
2 | 2 | 15 | 30 | ELBOW 90° DRENAJE 3" | 2 | 2 | 15 | 30 | ELBOW 90° DRENAJE 3"
1 | 1 | 45 | 45 | PVC CROSS DRENAJE 2" | 1 | 1 | 45 | 45 | PVC CROSS DRENAJE 2"
4 | 4 | 20 | 80 | TEE DRENAJE 2" | 4 | 4 | 20 | 80 | TEE DRENAJE 2"
3 | 3 | 120 | 360 | DRAINAGE TUBE 2" | 3 | 3 | 120 | 360 | DRAINAGE TUBE 2"
1 | 1 | 25 | 25 | SCREEN/CEDASO POR METRO | 1 | 1 | 25 | 25 | SCREEN/CEDASO POR METRO
1 | 1 | 100 | 100 | PVC GLUE 1/32 GAL. | 1 | 1 | 100 | 100 | PVC GLUE 1/32 GAL.
|  | SUB-TOTAL | 750 |  |  |  | SUB-TOTAL | 750
|  | TOTAL | 12902.5 |  |  |  | TOTAL | 12102.5

## 3 toilets and septic tank
AGUA PARA LA SALUD
2012-2013 |  |  | contribución de la aldea
|  |  |  | NOTAS | 1 QUINTAL DE HIERRO = 13 VARILLAS
Septic tank 3.5*2*1.5MTS Y POZO ASORCION | BAÑOS DE 3 CABINAS | cantidad total | precio por unidad | US $ | 6257.4194
DE LAVAMANO | DE CINCO |  |  | Quetzales | 48495
| CABINAS | TOTAL |  | precio total | descripción
|  | CANTID. | PRECIO |  | DESCRIPCION
4 | 2 | 6 | 225 | 1350 | ARENA DE RIO (POR M^3)
3 | 0 | 3 | 200 | 600 | PIEDRIN (POR M^3)
4 |  | 4 | 0 | 0 | EMPEDRADO (M^3)
30 | 15 | 45 | 75 | 3375 | CEMENTO (QUINTALES)
400 | 290 | 690 | 5.25 | 3622.5 | BLOCK DE 20*15*40
4 |  | 4 | 350 | 1400 | DOCENA REGLAS 8 pie -- 2" X 4"
0 |  | 0 | 350 | 0 | REGLAS 3x 3 (Docena)
4 |  | 4 | 250 | 1000 | DOCENA TABLAS DE 8 PIE
2 | 2 | 4 | 500 | 2000 | FLETE/ COMBUSTIBLE
1.5 | 1.5 | 3 | 1050 | 3150 | SUPERVISION/ ACCOUNTING/ DOCUMENTATION
6 | 4 | 10 | 600 | 6000 | VIATICOS
4 | 2 | 6 | 1200 | 7200 | MANO DE OBRA - ALBAÑIL 1 (POR SEMANA)
4 | 2 | 6 | 1200 | 7200 | MANO DE OBRA - ALBAÑIL 2 (POR SEMANA)
| 1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
|  | 0 | SUB-TOTAL | 38497.5
|  | 0 |  |  | MISC.
8 | 1 | 9 | 6 | 54 | ALAMBRE DE AMARRE (POR LIBRA)
3 | 0 | 3 | 350 | 1050 | ARMADURA 3/8" (POR QUINTAL)
|  | 0 | 325 | 0 | ARMADURA 1/4" (POR QUINTAL)
0 | 1 | 1 | 7 | 7 | CLAVOS PARA LAMINA (POR LIBRA)
3 | 1 | 4 | 6 | 24 | CLAVOS 3" (POR LIBRA)
1 | 1 | 2 | 20 | 40 | CEDASO POR METROS 23 CALIB
| 3 | 3 | 800 | 2400 | PUERTAS DE METAL 180+60CM
3 | 1 | 4 | 6 | 24 | CLAVOS 4" (POR LIBRA)
3 | 3 | 6 | 15 | 90 | CUBETAS DE ALBANIL
1 | 1 | 2 | 12 | 24 | CORTA HIERROS
3 | 3 | 6 | 45 | 270 | CANDADOS 3" BRONZA
0 | 6 | 6 | 65 | 390 | LAMINA DE 8" (UNIDAD)
|  | 0 | SUB-TOTAL | 4373
|  | 0 |  |  | HG
|  | 0 |  |  | DDDDDD
| 4 | 4 | 5 | 20 | CODO HG 90° 1/2"
| 4 | 4 | 5 | 20 | TEE HG 1/2
| 3 | 3 | 5 | 15 | ROLLOS DE TEFLON DE 3/4
| 2 | 2 | 5 | 10 | COPLA HG 1/2"
| 0 | 0 | 5 | 0 | LLAVE DE CHORRO 1/2" ( NIBICO O PP)
| 2 | 2 | 5 | 10 | LLAVE DE PASO 1/2" PVC
|  | 0 | 5 | 0 | NIPLE HG 1/2" X 2"
|  | 0 | 5 | 0 | NIPLE HG 1/2" 15CM
|  | 0 | 5 | 0 | NIPLE HG 1/2" 20 CM
|  | 0 | 5 | 0 | NIPLE HG 1/2" 100 CM
|  | 0 | 5 | 0 | NIPLE HG 1/2 120 CM
| 2 | 2 | 125 | 250 | TUBO HG 1/2"
| 0 | 0 | 5 | 0 | VALVULA DE FLOTE 1/2" HELBERT
| 0 | 0 | 5 | 0 | PICHACHA DE PVC DE TAPON
|  | 0 | SUB-TOTAL | 325
|  | 0 |  |  | PVC
| 1 | 1 | 2.5 | 2.5 | ADAPTADORA MACHO 1/2"
0 | 6 | 6 | 50 | 300 | FLANGE PVC PARA TASA CHINA
0 | 6 | 6 | 650 | 3900 | TASAS CHINA
0 | 6 | 6 | 35 | 210 | CERA PARA TASA CHINA
0 | 2 | 2 | 25 | 50 | CURVA PARA DRENAJE 90° 3"
0 | 3 | 3 | 14 | 42 | TORNILOS PARA TASAS CHINA
| 0 | 0 | 14 | 0 | CURVA PARA DRENAJE 90 2"
| 0 | 0 | 15 | 0 | TEE DRENAJE DE 2"
3 | 0 | 3 | 40 | 120 | ADAPTADOR HEMBRA 3"
3 | 0 | 3 | 25 | 75 | TAPON CON ROSCA DE 3"
|  | 0 | 30 | 0 | ADAPTADOR HEMBRA 2"
|  | 0 | 20 | 0 | TAPON CON ROSCA DE 2"
4 |  | 6 | 25 | 150 | TEE SANITARIO 3"
| 0 | 0 | 50 | 0 | CRUZ DRENAJE 2"
2 | 2 | 4 | 90 | 360 | TUBO BAJA PLUVIAL- DRENAJE 3"
|  | 0 | 48 | 0 | TUBO BAJA PLUVIAL- DRENAJE 2"
1 | 1 | 2 | 45 | 90 | PEGAMENTO 1/4 gal
|  |  | SUB-TOTAL | 5299.5
|  |  | TOTAL | 48495
Note on B33: estimation : 1Lb de clavos hace por 2 casas

## 2000 LITER -1 FAUCET
AGUA PARA LA SALUD
2012-2013
2000 LITER Tank no faucets | TOTAL QUANTITY | PRICE PER UNIT | US $ | 2285.2903
|  |  | Quetzales | 17711
| TOTAL |  | TOTAL PRICE | DESCRIPTION
| CANTID. | PRECIO |  | DESCRIPCION
APORTE DE LA COMUNIDAD
2.5 | 2.5 | 225 | 562.5 | RIVER SAND ( M^3)
2.5 | 2.5 | 200 | 500 | GRAVEL( M^3)
24 | 24 | 74 | 1776 | CEMENTO
8 | 8 |  | 0 | ROCK FOR BALAST(M^3) community
1 | 1 | 300 | 300 | WOOD 8 FEET --2" X 4" (DOZEN)
1.5 | 1.5 | 300 | 450 | WOOD BOARDS 8 FEET(DOZEN)
2.5 | 2.5 | 1200 | 3000 | SKILLED LABOR 1 (SEMANA)
1 | 1 | 750 | 750 | ACCOUNTING , DOCUMENTATION, DESIGN
2 | 2 | 1000 | 2000 | SUBSISTANCE
1 | 1 | 1400 | 1400 | SUPERVISION
1 | 1 | 2000 | 2000 | FREIGHT- GAS- COMMUNICATION
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
|  | SUB-TOTAL | 14338.5
MISC.
8 | 8 | 7 | 56 | TIE WIRE
25 | 25 | 25 | 625 | METERS OF SCREEN 1/4"
2 | 2 | 300 | 600 | RIENFORCING BAR 3/8"
2 | 2 | 7 | 14 | NAILS 2 1/2"
2 | 2 | 7 | 14 | NAILS 4"
1 | 1 | 75 | 75 | PADLOCK 2"
1 | 1 | 10 | 10 | HACK SAW BLADE
5 | 5 | 3 | 15 | ROLLS OF TEFLON
4 | 4 | 30 | 120 | MASONS BUCKETS
0.1 | 0.1 | 350 | 35 | PIPE THREADING OIL
0 | 0 | 800 | 0 | SECURITY DOORS
|  | SUB-TOTAL | 1564
HG
10 | 10 | 4.5 | 45 | ELBOWS GAL. 1/2"
11 | 11 | 3.5 | 38.5 | COPLING GAL. 1/2"
0 | 0 | 52 | 0 | FAUCET
1 | 1 | 20 | 20 | 1/2" PCV VALVE
2 | 2 | 125 | 250 | TUBO HG 1/2" (POR NIPLES)
1 | 1 | 35 | 35 | 1" HG Tee
1 | 1 | 45 | 45 | 12 X 50CM Niple HG
1 | 1 | 35 | 35 | 1" CODO HG
2 | 2 | 25 | 50 | REDUCTORES 1" X !/2"
1 | 1 | 196 | 196 | 1/2" FLOAT VALVE - HELBERT
4 | 4 | 22 | 88 | 2" DRAIN COVER-PVC
|  | SUB-TOTAL | 802.5
PVC
2 | 2 | 3 | 6 | 1/2" PVC ADAPTOR
4 | 4 | 23 | 92 | 2" MALE CAP PVC
4 | 4 | 7.61 | 30.44 | 2" FEMALE ADAPTOR
1 | 1 | 25 | 25 | 1/2" TUBE
4 | 4 | 4.9 | 19.6 | 2" ELBOW DRAINAGE
1 | 1 | 7 | 7 | 2" COPLING DRAINAGE
2 | 2 | 27.83 | 55.66 | 2" CROSS
3 | 3 | 6.1 | 18.3 | 2" TEE DRAINAGE
5 | 5 | 60 | 300 | 2" DRAINAGE TUBE
3 | 3 | 90 | 270 | 3" DRAINAGE TUBES FOR GUTTERS
2 | 2 | 20 | 40 | 3" DRAINAGE ELBOWS
1 | 1 | 22 | 22 | 3" DRAINAGE TEE
1 | 1 | 25 | 25 | SAND SCREEN
1 | 1 | 95 | 95 | GLUE 1/32 GALON
|  | SUB-TOTAL | 1006
|  | TOTAL | 17711

## 2000-TANQUE- WITH FAUCETS
AGUA PARA LA SALUD
ROTARY |  | 2012-2013
|  |  | NOTAS | OPTION #1, #2, and #3
Hand washing station with security doors 8 faucets with seepage pit | TOTAL QUANTITY | PRICE PER UNIT | US $ | 3441.0968
|  |  | Quetzales | 26668.5
| TOTAL |  | TOTAL PRICE | DESCRIPTION
| CANTID. | PRECIO |  | DESCRIPCION
APORTE DE LA COMUNIDAD
3 | 3 | 225 | 675 | RIVER SAND ( M^3)
3 | 3 | 200 | 600 | GRAVEL( M^3)
30 | 30 | 74 | 2220 | CEMENTO
8 | 8 |  | 0 | ROCK FOR BALAST(M^3) community
1 | 1 | 300 | 300 | WOOD 8 FEET --2" X 4" (DOZEN)
1.5 | 1.5 | 300 | 450 | WOOD BOARDS 8 FEET(DOZEN)
2 | 2 | 1200 | 2400 | SKILLED LABOR 1 (SEMANA)
2 | 2 | 1200 | 2400 | SKILLED LABOR 1 (SEMANA)
2 | 2 | 750 | 1500 | ACCOUNTING , DOCUMENTATION, DESIGN
4 | 4 | 1000 | 4000 | SUBSISTANCE
1 | 1 | 1400 | 1400 | SUPERVISION
1 | 1 | 2000 | 2000 | FREIGHT- GAS- COMMUNICATION
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
|  | SUB-TOTAL | 19545
MISC.
8 | 8 | 7 | 56 | TIE WIRE
25 | 25 | 25 | 625 | METERS OF SCREEN 1/4" |  | 2000 liter tank without security doors
3 | 3 | 300 | 900 | RIENFORCING BAR 3/8"
2 | 2 | 7 | 14 | NAILS 2 1/2"
2 | 2 | 7 | 14 | NAILS 4"
1 | 1 | 75 | 75 | PADLOCK 2"
1 | 1 | 10 | 10 | HACK SAW BLADE
5 | 5 | 3 | 15 | ROLLS OF TEFLON
4 | 4 | 30 | 120 | MASONS BUCKETS
0.1 | 0.1 | 350 | 35 | PIPE THREADING OIL
4 | 4 | 800 | 3200 | SECURITY DOORS
|  | SUB-TOTAL | 5064
HG
10 | 10 | 4.5 | 45 | ELBOWS GAL. 1/2"
11 | 11 | 3.5 | 38.5 | COPLING GAL. 1/2"
8 | 8 | 52 | 416 | FAUCET
1 | 1 | 20 | 20 | 1/2" PCV VALVE
2 | 2 | 125 | 250 | TUBO HG 1/2" (POR NIPLES)
1 | 1 | 196 | 196 | 1/2" FLOAT VALVE - HELBERT
4 | 4 | 22 | 88 | 2" DRAIN COVER-PVC
|  | SUB-TOTAL | 1053.5
PVC
2 | 2 | 3 | 6 | 1/2" PVC ADAPTOR
4 | 4 | 23 | 92 | 2" MALE CAP PVC
4 | 4 | 7.61 | 30.44 | 2" FEMALE ADAPTOR
1 | 1 | 25 | 25 | 1/2" TUBE
4 | 4 | 4.9 | 19.6 | 2" ELBOW DRAINAGE
1 | 1 | 7 | 7 | 2" COPLING DRAINAGE
2 | 2 | 27.83 | 55.66 | 2" CROSS
3 | 3 | 6.1 | 18.3 | 2" TEE DRAINAGE
5 | 5 | 60 | 300 | 2" DRAINAGE TUBE
3 | 3 | 90 | 270 | 3" DRAINAGE TUBES FOR GUTTERS
2 | 2 | 20 | 40 | 3" DRAINAGE ELBOWS
1 | 1 | 22 | 22 | 3" DRAINAGE TEE
1 | 1 | 25 | 25 | SAND SCREEN
1 | 1 | 95 | 95 | GLUE 1/32 GALON
|  | SUB-TOTAL | 1006 |  |  | 2000 liter tank with security doors option #1
|  | TOTAL | 26668.5
|  |  | NOTAS | WITHOUT SECURITY DOORS
Hand washing station 8 faucets without security doors | TOTAL QUANTITY | PRICE PER UNIT | US $ | 2515.5921
|  |  | Quetzales | 19118.5
| TOTAL |  | TOTAL PRICE | DESCRIPTION
| CANTID. | PRECIO |  | DESCRIPCION
APORTE DE LA COMUNIDAD
3 | 3 | 225 | 675 | RIVER SAND ( M^3)
3 | 3 | 200 | 600 | GRAVEL( M^3)
30 | 30 | 74 | 2220 | CEMENTO
8 | 8 |  | 0 | ROCK FOR BALAST(M^3) community
1 | 1 | 300 | 300 | WOOD 8 FEET --2" X 4" (DOZEN)
1.5 | 1.5 | 300 | 450 | WOOD BOARDS 8 FEET(DOZEN)
2.25 | 2.25 | 1200 | 2700 | SKILLED LABOR
2 | 2 | 750 | 1500 | TRAINEE
3 | 3 | 750 | 2250 | SUBSISTANCE
1 | 1 | 1400 | 1400 | SUPERVISION
1 | 1 | 1500 | 1500 | FREIGHT- GAS- COMMUNICATION
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING ; AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
|  | SUB-TOTAL | 15195 |  | 2000 Liter tank with 8 faucets wall and security doors option #2
MISC.
8 | 8 | 7 | 56 | TIE WIRE |  |  | OPTIONS DEPEND ON SPACE AVAILABLE
25 | 25 | 25 | 625 | METERS OF SCREEN 1/4"
3 | 3 | 300 | 900 | RIENFORCING BAR 3/8"
2 | 2 | 7 | 14 | NAILS 2 1/2"
2 | 2 | 7 | 14 | NAILS 4"
1 | 1 | 75 | 75 | PADLOCK 2"
1 | 1 | 10 | 10 | HACK SAW BLADE
5 | 5 | 3 | 15 | ROLLS OF TEFLON
4 | 4 | 30 | 120 | MASONS BUCKETS
0.1 | 0.1 | 350 | 35 | PIPE THREADING OIL
0 | 0 | 800 | 0 | SECURITY DOORS
|  | SUB-TOTAL | 1864
HG
10 | 10 | 4.5 | 45 | ELBOWS GAL. 1/2"
11 | 11 | 3.5 | 38.5 | COPLING GAL. 1/2"
8 | 8 | 52 | 416 | FAUCET
1 | 1 | 20 | 20 | 1/2" PCV VALVE
2 | 2 | 125 | 250 | TUBO HG 1/2" (POR NIPLES)
1 | 1 | 196 | 196 | 1/2" FLOAT VALVE - HELBERT
4 | 4 | 22 | 88 | 2" DRAIN COVER-PVC
|  | SUB-TOTAL | 1053.5
PVC
2 | 2 | 3 | 6 | 1/2" PVC ADAPTOR
4 | 4 | 23 | 92 | 2" MALE CAP PVC
4 | 4 | 7.61 | 30.44 | 2" FEMALE ADAPTOR
1 | 1 | 25 | 25 | 1/2" TUBE | 2000 Liter tank with 6 faucets wall and security doors option #3
4 | 4 | 4.9 | 19.6 | 2" ELBOW DRAINAGE
1 | 1 | 7 | 7 | 2" COPLING DRAINAGE
2 | 2 | 27.83 | 55.66 | 2" CROSS
3 | 3 | 6.1 | 18.3 | 2" TEE DRAINAGE
5 | 5 | 60 | 300 | 2" DRAINAGE TUBE
3 | 3 | 90 | 270 | 3" DRAINAGE TUBES FOR GUTTERS
2 | 2 | 20 | 40 | 3" DRAINAGE ELBOWS
1 | 1 | 22 | 22 | 3" DRAINAGE TEE
1 | 1 | 25 | 25 | SAND SCREEN
1 | 1 | 95 | 95 | GLUE 1/32 GALON
|  | SUB-TOTAL | 1006
|  | TOTAL | 19118.5

## 5000 Rain w-faucets
AGUA PARA LA SALUD |  |  |  | NOTAS
ROTARY |  | 2012-2013
5000 LITER RAIN STORAGE | 8 | TOTAL QUANTITY | PRICE PER UNIT | US $ | 5041.4116
| FAUCET |  |  | Quetzales | 39070.94
| HAND | TOTAL |  | TOTAL PRICE | DESCRIPTION
| WASH | CANTID. | PRECIO |  | DESCRIPCION
APORTE DE LA COMUNIDAD
6 | 2 | 8 | 225 | 1800 | RIVER SAND ( M^3)
6 | 2 | 8 | 200 | 1600 | GRAVEL( M^3)
40 | 20 | 60 | 74 | 4440 | CEMENTO
8 | 6 | 14 |  | 0 | ROCK FOR BALAST(M^3) community
1 | 1 | 2 | 300 | 600 | WOOD 8 FEET --2" X 4" (DOZEN)
1.5 | 1.5 | 3 | 300 | 900 | WOOD BOARDS 8 FEET(DOZEN)
2 | 1 | 3 | 1200 | 3600 | SKILLED LABOR 1 (SEMANA)
3 | 1 | 4 | 1200 | 4800 | SKILLED LABOR 1 (SEMANA)
3 | 1 | 4 | 750 | 3000 | ACCOUNTING , DOCUMENTATION, DESIGN
3 | 1 | 4 | 1000 | 4000 | SUBSISTANCE
1 | 1 | 2 | 1400 | 2800 | SUPERVISION
| 1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
1 | 1 | 2 | 2000 | 4000 | FREIGHT- GAS- COMMUNICATION
|  | 0 | SUB-TOTAL | 33140
|  | 0 |  |  | MISC.
8 | 5 | 13 | 7 | 91 | TIE WIRE
35 | 0 | 35 | 20 | 700 | METERS OF SCREEN 1/4"
5 | 1 | 6 | 300 | 1800 | RIENFORCING BAR 3/8"
2 | 1 | 3 | 7 | 21 | NAILS 2 1/2"
2 | 1 | 3 | 7 | 21 | NAILS 4"
0 | 2 | 2 | 75 | 150 | PADLOCK 2"
1 | 1 | 2 | 10 | 20 | HACK SAW BLADE
5 | 5 | 10 | 3 | 30 | ROLLS OF TEFLON
4 | 3 | 7 | 30 | 210 | MASONS BUCKETS
| 2 | 2 | 500 | 1000 | SECURTITY DOORS
0.1 | 0.1 | 0.2 | 350 | 70 | PIPE THREADING OIL
|  | 0 | SUB-TOTAL | 4113
|  | 0 |  |  | HG
4 | 4 | 8 | 4.5 | 36 | ELBOWS GAL. 1/2"
2 | 11 | 13 | 3.5 | 45.5 | COPLING GAL. 1/2"
1 |  | 1 | 20 | 20 | 1/2" PCV VALVE
1 | 1 | 2 | 125 | 250 | TUBO HG 1/2" (POR NIPLES)
| 1 | 1 | 190 | 190 | TUBO HG 1" (POR NIPLES)
2 | 4 | 6 | 20 | 120 | ELBOWS GAL. 1"
| 2 | 2 | 18 | 36 | REDUCER 1 " X 1/2"
1 |  | 1 | 196 | 196 | 1/2" FLOAT VALVE - HELBERT
4 |  | 4 | 22 | 88 | 2" DRAIN COVER-PVC
|  | 0 | SUB-TOTAL | 981.5
|  | 0 |  |  | PVC
2 |  | 2 | 3 | 6 | 1/2" PVC ADAPTOR
4 |  | 4 | 23 | 92 | 2" MALE CAP PVC WITH THREADS
4 |  | 4 | 7.61 | 30.44 | 2" FEMALE ADAPTOR
1 |  | 1 | 25 | 25 | 1/2" TUBE PVC
4 |  | 4 | 4.9 | 19.6 | 2" ELBOW DRAINAGE
1 |  | 1 | 7 | 7 | 2" COPLING DRAINAGE
0 | 4 | 4 | 6.1 | 24.4 | 2" TEE DRAINAGE
1 | 2 | 3 | 60 | 180 | 2" DRAINAGE TUBE
3 |  | 3 | 90 | 270 | 3" DRAINAGE TUBE
2 |  | 2 | 20 | 40 | 3" DRAINAGE ELBOWS
1 |  | 1 | 22 | 22 | 3" DRAINAGE TEE
1 |  | 1 | 25 | 25 | SAND SCREEN
1 |  | 1 | 95 | 95 | GLUE 1/32 GALON
|  |  | SUB-TOTAL | 836.44
|  |  | TOTAL | 39070.94

## 10,000 RAIN
AGUA PARA LA SALUD
2012-2013
10,000 LITER RAIN STORAGE- RAISED 1 METER | TOTAL QUANTITY | PRICE PER UNIT | US $ | 4781.0116
|  |  | Quetzales | 37052.84
| TOTAL |  | TOTAL PRICE | DESCRIPTION
| CANTID. | PRECIO |  | DESCRIPCION
APORTE DE LA COMUNIDAD
10 | 10 | 225 | 2250 | RIVER SAND ( M^3)
4 | 4 | 200 | 800 | GRAVEL( M^3)
50 | 50 | 74 | 3700 | CEMENTO
15 | 15 |  | 0 | ROCK FOR BALAST(M^3) community
2 | 2 | 300 | 600 | WOOD 8 FEET --2" X 4" (DOZEN)
3 | 3 | 300 | 900 | WOOD BOARDS 8 FEET(DOZEN)
4 | 4 | 1200 | 4800 | SKILLED LABOR 1 (SEMANA)
4 | 4 | 1200 | 4800 | SKILLED LABOR 1 (SEMANA)
3 | 3 | 750 | 2250 | ACCOUNTING , DOCUMENTATION, DESIGN
4 | 4 | 1000 | 4000 | SUBSISTANCE
1 | 1 | 1400 | 1400 | SUPERVISION
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
1 | 1 | 2000 | 2000 | FREIGHT- GAS- COMMUNICATION
|  | SUB-TOTAL | 29100
MISC.
26 | 26 | 7 | 182 | TIE WIRE
35 | 35 | 25 | 875 | METERS OF SCREEN 1/4"
7 | 7 | 300 | 2100 | RIENFORCING BAR 3/8"
4 | 4 | 7 | 28 | NAILS 2 1/2"
4 | 4 | 7 | 28 | NAILS 4"
1 | 1 | 75 | 75 | PADLOCK 2"
1 | 1 | 10 | 10 | HACK SAW BLADE
5 | 5 | 3 | 15 | ROLLS OF TEFLON
6 | 6 | 30 | 180 | MASONS BUCKETS
0.1 | 0.1 | 350 | 35 | PIPE THREADING OIL
|  | SUB-TOTAL | 3528
HG
10 | 10 | 4.5 | 45 | ELBOWS GAL. 1/2"
11 | 11 | 3.5 | 38.5 | COPLING GAL. 1/2"
6 | 6 | 250 | 1500 | 1" HG TUBES
1 | 1 | 20 | 20 | 1/2" PCV VALVE
2 | 2 | 125 | 250 | TUBO HG 1/2" (POR NIPLES)
1 | 1 | 196 | 196 | 1/2" FLOAT VALVE - HELBERT
0 | 0 | 22 | 0 | 2" DRAIN COVER-PVC
|  | SUB-TOTAL | 2049.5
PVC
2 | 2 | 3 | 6 | 1/2" PVC ADAPTOR
4 | 4 | 23 | 92 | 2" MALE CAP PVC
4 | 4 | 7.61 | 30.44 | 2" FEMALE ADAPTOR
2 | 2 | 25 | 50 | 1/2" TUBE
4 | 4 | 4.9 | 19.6 | 2" ELBOW DRAINAGE
1 | 1 | 7 | 7 | 2" COPLING DRAINAGE
3 | 3 | 6.1 | 18.3 | 2" TEE DRAINAGE
0 | 0 | 60 | 0 | 2" DRAINAGE TUBE
16 | 16 | 110 | 1760 | 3" DRAINAGE TUBE
7 | 7 | 20 | 140 | 3" DRAINAGE ELBOWS
6 | 6 | 22 | 132 | 3" DRAINAGE TEE
1 | 1 | 25 | 25 | SAND SCREEN
1 | 1 | 95 | 95 | GLUE 1/32 GALON
|  | SUB-TOTAL | 2375.34
|  | TOTAL | 37052.84

## 5,000 RAIN
AGUA PARA LA SALUD
2012-2013
5000 LITER RAIN STORAGE | TOTAL QUANTITY | PRICE PER UNIT | US $ | 3743.4632
|  |  | Quetzales | 29011.84
| TOTAL |  | TOTAL PRICE | DESCRIPTION
| CANTID. | PRECIO |  | DESCRIPCION
APORTE DE LA COMUNIDAD
6 | 6 | 225 | 1350 | RIVER SAND ( M^3)
6 | 6 | 200 | 1200 | GRAVEL( M^3)
40 | 40 | 74 | 2960 | CEMENTO
8 | 8 |  | 0 | ROCK FOR BALAST(M^3) community
1 | 1 | 300 | 300 | WOOD 8 FEET --2" X 4" (DOZEN)
1.5 | 1.5 | 300 | 450 | WOOD BOARDS 8 FEET(DOZEN)
3 | 3 | 1200 | 3600 | SKILLED LABOR 1 (SEMANA)
3 | 3 | 1200 | 3600 | SKILLED LABOR 1 (SEMANA)
3 | 3 | 750 | 2250 | ACCOUNTING , DOCUMENTATION, DESIGN
4 | 4 | 1000 | 4000 | SUBSISTANCE
1 | 1 | 1400 | 1400 | SUPERVISION
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
1 | 1 | 2000 | 2000 | FREIGHT- GAS- COMMUNICATION
|  | SUB-TOTAL | 24710
MISC.
8 | 8 | 7 | 56 | TIE WIRE
35 | 35 | 25 | 875 | METERS OF SCREEN 1/4"
5 | 5 | 300 | 1500 | RIENFORCING BAR 3/8"
2 | 2 | 7 | 14 | NAILS 2 1/2"
2 | 2 | 7 | 14 | NAILS 4"
1 | 1 | 75 | 75 | PADLOCK 2"
1 | 1 | 10 | 10 | HACK SAW BLADE
5 | 5 | 3 | 15 | ROLLS OF TEFLON
4 | 4 | 30 | 120 | MASONS BUCKETS
0.1 | 0.1 | 350 | 35 | PIPE THREADING OIL
|  | SUB-TOTAL | 2714
HG
10 | 10 | 4.5 | 45 | ELBOWS GAL. 1/2"
11 | 11 | 3.5 | 38.5 | COPLING GAL. 1/2"
1 | 1 | 20 | 20 | 1/2" PCV VALVE
2 | 2 | 125 | 250 | TUBO HG 1/2" (POR NIPLES)
1 | 1 | 196 | 196 | 1/2" FLOAT VALVE - HELBERT
4 | 4 | 22 | 88 | 2" DRAIN COVER-PVC
|  | SUB-TOTAL | 637.5
PVC
2 | 2 | 3 | 6 | 1/2" PVC ADAPTOR
4 | 4 | 23 | 92 | 2" MALE CAP PVC
4 | 4 | 7.61 | 30.44 | 2" FEMALE ADAPTOR
1 | 1 | 25 | 25 | 1/2" TUBE
4 | 4 | 4.9 | 19.6 | 2" ELBOW DRAINAGE
1 | 1 | 7 | 7 | 2" COPLING DRAINAGE
3 | 3 | 6.1 | 18.3 | 2" TEE DRAINAGE
5 | 5 | 60 | 300 | 2" DRAINAGE TUBE
3 | 3 | 90 | 270 | 3" DRAINAGE TUBE
2 | 2 | 20 | 40 | 3" DRAINAGE ELBOWS
1 | 1 | 22 | 22 | 3" DRAINAGE TEE
1 | 1 | 25 | 25 | SAND SCREEN
1 | 1 | 95 | 95 | GLUE 1/32 GALON
|  | SUB-TOTAL | 950.34
|  | TOTAL | 29011.84

## SEPTIC TANK
AGUA PARA LA SALUD
2012-2013
|  |  | NOTAS | 1 QUINTAL DE HIERRO = 13 VARILLAS
Septic tank 5,75*320CM | cantidad total | precio por unidad | US $ | 4427.7419
DE LAVAMANO |  |  | Quetzales | 34315
| TOTAL |  | precio total | descripción
| CANTID. | PRECIO |  | DESCRIPCION
4 | 4 | 160 | 640 | ARENA DE RIO (POR M^3)
3 | 3 | 125 | 375 | PIEDRIN (POR M^3)
3 | 3 | 0 | 0 | EMPEDRADO (M^3)
40 | 40 | 74 | 2960 | CEMENTO (QUINTALES)
550 | 550 | 5 | 2750 | BLOCK DE 20*15*40
0 | 0 | 0 | 0 | REGLAS 5 VARAS 2" X 4" (UNIDAD)
4 | 4 | 0 | 0 | REGLAS 3x 3 (Docena)
4 | 4 | 0 | 0 | DOCENA TABLAS DE 2 1/2 VARAS(IUNIDAD )
2 | 2 | 2000 | 4000 | FLETE
6 | 6 | 750 | 4500 | ADMINISTRACION
1.5 | 1.5 | 1400 | 2100 | SUPERVISION
6 | 6 | 1000 | 6000 | VIATICOS
3 | 3 | 1200 | 3600 | MANO DE OBRA - ALBAÑIL 1 (POR SEMANA)
3 | 3 | 1200 | 3600 | MANO DE OBRA - ALBAÑIL 2 (POR SEMANA)
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
| 0 | SUB-TOTAL | 32125
| 0 |  |  | MISC.
10 | 10 | 6 | 60 | ALAMBRE DE AMARRE (POR LIBRA)
4 | 4 | 310 | 1240 | ARMADURA 3/8" (POR QUINTAL)
| 0 | 265 | 0 | ARMADURA 1/4" (POR QUINTAL)
1 | 1 | 7 | 7 | CLAVOS PARA LAMINA (POR LIBRA)
3 | 3 | 6 | 18 | CLAVOS 3" (POR LIBRA)
1 | 1 | 20 | 20 | CEDASO POR METROS 23 CALIB
| 0 | 850 | 0 | PUERTAS DE METAL 180+60CM
3 | 3 | 6 | 18 | CLAVOS 4" (POR LIBRA)
3 | 3 | 15 | 45 | CUBETAS DE ALBANIL
1 | 1 | 12 | 12 | CORTA HIERROS
3 | 3 | 45 | 135 | CANDADOS 3" BRONZA
0 | 0 | 65 | 0 | LAMINA DE 8" (UNIDAD)
| 0 | SUB-TOTAL | 1555
| 0 |  |  | HG
| 0 |  |  | DDDDDD
| 0 | 0 | 0 | CODO HG 90° 1/2"
| 0 | 0 | 0 | TEE HG 1/2
| 0 | 0 | 0 | ROLLOS DE TEFLON DE 3/4
| 0 | 0 | 0 | COPLA HG 1/2"
| 0 | 0 | 0 | LLAVE DE CHORRO 1/2" ( NIBICO O PP)
| 0 | 0 | 0 | LLAVE DE PASO 1/2" (ITALIANO)
| 0 | 0 | 0 | NIPLE HG 1/2" 10 CM
| 0 | 0 | 0 | NIPLE HG 1/2" 15CM
| 0 | 0 | 0 | NIPLE HG 1/2" 20 CM
| 0 | 0 | 0 | NIPLE HG 1/2" 100 CM
| 0 | 0 | 0 | NIPLE HG 1/2 120 CM
| 0 | 0 | 0 | TUBO HG 1/2"
| 0 | 0 | 0 | VALVULA DE FLOTE 1/2" HELBERT
| 0 | 0 | 0 | PICHACHA DE PVC DE TAPON
| 0 | SUB-TOTAL | 0
| 0 |  |  | PVC
| 0 | 2.5 | 0 | ADAPTADORA MACHO 1/2"
0 | 0 | 50 | 0 | ANILLO PVC PARA TASA CHINA
0 | 0 | 550 | 0 | TASAS CHINA
0 | 0 | 35 | 0 | CERA PARA TASA CHINA
0 | 0 | 25 | 0 | CURVA PARA DRENAJE 90° 3"
0 | 0 | 14 | 0 | TORNILOS PARA TASAS CHINA
| 0 | 14 | 0 | CURVA PARA DRENAJE 90 2"
| 0 | 15 | 0 | TEE DRENAJE DE 2"
3 | 3 | 40 | 120 | ADAPTADOR HEMBRA 3"
3 | 3 | 25 | 75 | TAPON CON ROSCA DE 3"
5 | 5 | 25 | 125 | TEE SANITARIO 3"
| 0 | 50 | 0 | CRUZ DRENAJE 2"
3 | 3 | 90 | 270 | TUBO BAJA PLUVIAL- DRENAJE 3"
| 0 | 48 | 0 | TUBO BAJA PLUVIAL- DRENAJE 2"
1 | 1 | 45 | 45 | PEGAMENTO 1/4 gal
|  | SUB-TOTAL | 635
|  | TOTAL | 34315

## PUMP
AGUA PARA LA SALUD
2012-2013
PUMP SYSTEM | TOTAL QUANTITY | PRICE PER UNIT | US $ | 1108.6452
|  |  | Quetzales | 8592
| TOTAL |  | TOTAL PRICE | DESCRIPTION
| CANTID. | PRECIO |  | DESCRIPCION
0.5 | 0.5 | 225 | 112.5 | RIVER SAND ( M^3)
0.5 | 0.5 | 200 | 100 | GRAVEL( M^3)
4 | 4 | 74 | 296 | CEMENTO
1 | 1 |  | 0 | ROCK FOR BALAST(M^3) community
0.2 | 0.2 | 300 | 60 | WOOD 8 FEET --2" X 4" (DOZEN)
0.2 | 0.2 | 300 | 60 | WOOD BOARDS 8 FEET(DOZEN)
1 | 1 | 1200 | 1200 | SKILLED LABOR 1 (SEMANA)
0.25 | 0.25 | 750 | 187.5 | ACCOUNTING , DOCUMENTATION, DESIGN
0.5 | 0.5 | 1000 | 500 | SUBSISTANCE
0.5 | 0.5 | 1400 | 700 | SUPERVISION
0.5 | 0.5 | 2000 | 1000 | FREIGHT-GAS - COMMUNICATION
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
|  | SUB-TOTAL | 5816
MISC.
1 | 1 | 7 | 7 | TIE WIRE
0.25 | 0.25 | 300 | 75 | IRON RE-BAR 3/8" (POR QUINTAL)
1 | 1 | 7 | 7 | NAILS 2 1/2" (POR LIBRA)
1 | 1 | 7 | 7 | NAILS 4" (POR LIBRA)
1 | 1 | 10 | 10 | HACK SAW BLADE
2 | 2 | 2.5 | 5 | ROLLS OF TEFLON
2 | 2 | 20 | 40 | MASONS BUCKETS
1 | 1 | 1200 | 1200 | ANAUGER #900 PUMP
0 | 0 | 800 | 0 | SECURITY DOORS
|  | SUB-TOTAL | 1351
HG
2 | 2 | 20 | 40 | ELBOW HG 90° 1"
1 | 1 | 5 | 5 | UNIVERSAL COUPLING HG 1" PVC
0 | 0 | 52 | 0 | FAUCETS 1/2" ( NIBICO O PP)
0 | 0 | 20 | 0 | VALVE 1/2" PVC
1 | 1 | 250 | 250 | ROLL POLYDUCTAL TUBING 1"
1 | 1 | 25 | 25 | TEE HG 1"
1 | 1 | 75 | 75 | CANDADO
|  | SUB-TOTAL | 395
PVC
2 | 2 | 15 | 30 | FEMALE ADAPTOR 1" POLYDUCTAL
50 | 50 | 15 | 750 | #12 X 3 ELECTRICAL CABLE
1 | 1 | 150 | 150 | FLOAT LEVEL CONTROL
1 | 1 | 100 | 100 | PVC GLUE 1/32 GAL.
|  | SUB-TOTAL | 1030
|  | TOTAL | 8592

## LATRINES (3)
AGUA PARA LA SALUD
2012-2013
NOTAS
SCHOOL LATRINE 3 CABINS | TOTAL QUANTITY | PRICE PER UNIT | US $ | 2548.6452
|  |  | Quetzales | 19752
| TOTAL |  | TOTAL PRICE | DESCRIPTION
| CANTID. | PRECIO |  | DESCRIPCION
2 | 2 | 225 | 450 | RIVER SAND ( M^3)
1.5 | 1.5 | 200 | 300 | GRAVEL( M^3)
20 | 20 | 74 | 1480 | CEMENTO
275 | 275 | 5 | 1375 | BLOCK 20*15*40
3 | 3 |  | 0 | ROCK FOR BALAST(M^3) community
0.2 | 0.2 | 300 | 60 | WOOD 8 FEET --2" X 4" (DOZEN)
0.2 | 0.2 | 300 | 60 | WOOD 10 FEET 3"X4" (DOZEN)
0.6 | 0.6 | 300 | 180 | WOOD BOARDS 8 FEET(DOZEN)
3 | 3 | 80 | 240 | LATRINE POTS
1 | 1 | 750 | 750 | ACCOUNTING, DESIGN, DOCUMENTATION
2 | 2 | 1200 | 2400 | SKILLED LABOR 1 (SEMANA)
2 | 2 | 1200 | 2400 | SUBSISTANCE
1 | 1 | 1400 | 1400 | SUPERVISION
1 | 1 | 2000 | 2000 | FREIGHT, GAS, COMMUNICATIONS
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
|  | SUB-TOTAL | 14695
MISC.
4 | 4 | 7 | 28 | IRON TIE WIRE
3 | 3 | 300 | 900 | IRON REINFORCING BARS 3/8"
10 | 10 | 15 | 150 | IRON REINFORCING BARS 1/4"
1 | 1 | 7 | 7 | ROOF METAL NAILS
1 | 1 | 7 | 7 | NAILS 2 1/2"
1 | 1 | 7 | 7 | NAILS 4 "
6 | 6 | 100 | 600 | GALVANIZED ROOF METAL 8"
3 | 3 | 900 | 2700 | DOORS 180x60cm (c/u)
4 | 4 | 20 | 80 | BUCKETS
|  | SUB-TOTAL | 4479
PVC
2 | 2 | 35 | 70 | COUPLING PVC 3"
2 | 2 | 24 | 48 | ELBOW PVC DRAIN - 90° - 3"
3 | 3 | 120 | 360 | DRAIN TUBES 3"
1 | 1 | 100 | 100 | PVC GLUE 1/8 GAL.
| 0 |  | 0
|  | SUB-TOTAL | 578
|  | TOTAL | 19752

## LATRINES(5)
AGUA PARA LA SALUD
2012-2013
contribución de la aldea
|  |  | NOTAS | 1 QUINTAL DE HIERRO = 13 VARILLAS
LATRINES DE 5 CABINAS | cantidad total | precio por unidad | US $ | 5101.2258
DE CINCO |  |  | Quetzales | 39534.5
CABINAS | TOTAL |  | precio total | descripción
| CANTID. | PRECIO |  | DESCRIPCION
3 | 3 | 225 | 675 | ARENA DE RIO (POR M^3)
1 | 1 | 200 | 200 | PIEDRIN (POR M^3)
4 | 4 | 0 | 0 | EMPEDRADO (M^3)
20 | 20 | 74 | 1480 | CEMENTO (QUINTALES)
425 | 425 | 5 | 2125 | BLOCK DE 20*15*40
1 | 1 | 300 | 300 | REGLAS 5 VARAS 2" X 4" (UNIDAD)
| 0 | 0 | 0 | REGLAS 3x 3 (Docena)
| 0 | 0 | 0 | DOCENA TABLAS DE 2 1/2 VARAS(IUNIDAD )
5 | 5 | 80 | 400 | LATRINE POTS
2 | 2 | 2000 | 4000 | FLETE, GAS, COMMUNICATIONS
6 | 6 | 750 | 4500 | ACCOUNTING, DESIGN, DOCUMENTATION
1.5 | 1.5 | 1400 | 2100 | SUPERVISION
6 | 6 | 1000 | 6000 | VIATICOS
3 | 3 | 1200 | 3600 | MANO DE OBRA - ALBAÑIL 1 (POR SEMANA)
3 | 3 | 1200 | 3600 | MANO DE OBRA - ALBAÑIL 2 (POR SEMANA)
1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
| 0 | SUB-TOTAL | 30580
| 0 |  |  | MISC.
1 | 1 | 6 | 6 | ALAMBRE DE AMARRE (POR LIBRA)
0 | 0 | 310 | 0 | ARMADURA 3/8" (POR QUINTAL)
| 0 | 265 | 0 | ARMADURA 1/4" (POR QUINTAL)
1 | 1 | 7 | 7 | CLAVOS PARA LAMINA (POR LIBRA)
1 | 1 | 6 | 6 | CLAVOS 3" (POR LIBRA)
1 | 1 | 20 | 20 | CEDASO POR METROS 23 CALIB
5 | 5 | 850 | 4250 | PUERTAS DE METAL 180+60CM
1 | 1 | 6 | 6 | CLAVOS 4" (POR LIBRA)
3 | 3 | 15 | 45 | CUBETAS DE ALBANIL
1 | 1 | 12 | 12 | CORTA HIERROS
5 | 5 | 45 | 225 | CANDADOS 3" BRONZA
10 | 10 | 65 | 650 | LAMINA DE 8" (UNIDAD)
| 0 | SUB-TOTAL | 5227
| 0 |  |  | HG
| 0 |  |  | DDDDDD
6 | 6 | 5 | 30 | CODO HG 90° 1/2"
5 | 5 | 5 | 25 | TEE HG 1/2
3 | 3 | 5 | 15 | ROLLOS DE TEFLON DE 3/4
2 | 2 | 5 | 10 | COPLA HG 1/2"
0 | 0 | 75 | 0 | LLAVE DE CHORRO 1/2" ( NIBICO O PP)
2 | 2 | 0 | 0 | LLAVE DE PASO 1/2" (ITALIANO)
| 0 | 0 | 0 | NIPLE HG 1/2" 10 CM
| 0 | 0 | 0 | NIPLE HG 1/2" 15CM
| 0 | 0 | 0 | NIPLE HG 1/2" 20 CM
| 0 | 0 | 0 | NIPLE HG 1/2" 100 CM
| 0 | 0 | 0 | NIPLE HG 1/2 120 CM
1 | 1 | 125 | 125 | TUBO HG 1/2"
0 | 0 | 240 | 0 | VALVULA DE FLOTE 1/2" HELBERT
0 | 0 | 35 | 0 | PICHACHA DE PVC DE TAPON
| 0 | SUB-TOTAL | 205
| 0 |  |  | PVC
1 | 1 | 2.5 | 2.5 | ADAPTADORA MACHO 1/2"
5 | 5 | 50 | 250 | ANILLO PVC PARA TASA CHINA
5 | 5 | 550 | 2750 | TASAS CHINA
5 | 5 | 35 | 175 | CERA PARA TASA CHINA
2 | 2 | 25 | 50 | CURVA PARA DRENAJE 90° 3"
5 | 5 | 14 | 70 | TORNILOS PARA TASAS CHINA
0 | 0 | 14 | 0 | CURVA PARA DRENAJE 90 2"
0 | 0 | 15 | 0 | TEE DRENAJE DE 2"
0 | 0 | 40 | 0 | ADAPTADOR HEMBRA 3"
0 | 0 | 25 | 0 | TAPON CON ROSCA DE 3"
| 0 | 25 | 0 | TEE SANITARIO 3"
0 | 0 | 50 | 0 | CRUZ DRENAJE 2"
2 | 2 | 90 | 180 | TUBO BAJA PLUVIAL- DRENAJE 3"
| 0 | 48 | 0 | TUBO BAJA PLUVIAL- DRENAJE 2"
1 | 1 | 45 | 45 | PEGAMENTO 1/4 gal
|  | SUB-TOTAL | 3522.5
|  | TOTAL | 39534.5
Note on A37: estimation : 1Lb de clavos hace por 2 casas

## Flush (5)
AGUA PARA LA SALUD
2012-2013
Aldea:
Sector:
Fecha: |  |  |  | contribución de la aldea
|  |  |  | NOTAS | 1 QUINTAL DE HIERRO = 13 VARILLAS
Septic tank | Flush de 5 cabinas | cantidad total | precio por unidad | US $ | 6073.2581
DE LAVAMANO | DE CINCO |  |  | Quetzales | 47067.75
| CABINAS | TOTAL |  | precio total | descripción
|  | CANTID. | PRECIO |  | DESCRIPCION
3 | 3 | 6 | 225 | 1350 | ARENA DE RIO (POR M^3)
2 | 2 | 4 | 200 | 800 | PIEDRIN (POR M^3)
3 | 4 | 7 | 0 | 0 | EMPEDRADO (M^3)
25 | 30 | 55 | 74 | 4070 | CEMENTO (QUINTALES)
345 | 425 | 770 | 4.6 | 3542 | BLOCK DE 20*15*40
4 | 1 | 5 | 300 | 1500 | REGLAS 5 VARAS 2" X 4" (UNIDAD)
3 | 1 | 4 | 300 | 1200 | REGLAS 3x 3 X 3 VARAS (Docena)
3 | 1 | 4 | 300 | 1200 | DOCENA TABLAS DE 2 1/2 VARAS(IUNIDAD )
|  | 0 | 0 | 0 | DOCENAS DE TABLAS 3 VARAS (DOCENA )
1 | 1 | 2 | 2000 | 4000 | TRANSPORTATION, COMMUNICTIONS
1 | 1 | 2 | 750 | 1500 | ACCOUNTING , DOCUMENTATION, DESIGN
1 | 1 | 2 | 1400 | 2800 | SUPERVISION
3 | 2 | 5 | 1200 | 6000 | MANO DE OBRA - ALBAÑIL 1 (POR SEMANA)
3 | 2 | 5 | 1200 | 6000 | MANO DE OBRA - ALBAÑIL 2 (POR SEMANA)
| 1 | 1 | 1600 | 1600 | FIRST YEAR COST OF REPORTING AND SUSTAINABILTY VISITS AND REPORTING FOR THREE YEARS AFTER PROJECT CLOSE
|  | 0 | SUB-TOTAL | 35562
|  | 0 |  |  | MISC.
8 | 8 | 16 | 7 | 112 | ALAMBRE DE AMARRE (POR LIBRA)
3 | 4 | 7 | 265 | 1855 | ARMADURA 3/8" (POR QUINTAL)
| 1.2 | 1.2 | 265 | 318 | ARMADURA 1/4" (POR QUINTAL)
| 2 | 2 | 7 | 14 | CLAVOS PARA LAMINA (POR LIBRA)
3 | 1 | 4 | 7 | 28 | CLAVOS 3" (POR LIBRA)
3 | 1 | 4 | 7 | 28 | CLAVOS 4" (POR LIBRA)
5 | 0 | 5 | 55 | 275 | CANDADOS 3" BRONZA
| 5 | 5 | 500 | 2500 | TOILETS CHINA
| 5 | 5 | 60 | 300 | FLANGE, WAX RING
| 10 | 10 | 75 | 750 | LAMINA DE 8" (UNIDAD)
| 5 | 5 | 850 | 4250 | PUERTAS DE 180x60cm (c/u)
|  | 0 | SUB-TOTAL | 10430
|  | 0 |  |  | HG
|  | 0 | 5 | 0 | CODO HG 90° 1/2"
|  | 0 | 5 | 0 | COPLA HG 1/2"
|  | 0 | 65 | 0 | LLAVE DE CHORRO 1/2" ( NIBICO O PP)
|  | 0 | 60 | 0 | LLAVE DE PASO 1/2" (ITALIANO)
|  | 0 | 75 | 0 | LLAVE COMPUERTA 1/2" NIBICO O PP
|  | 0 | 0 | 0 | NIPLE HG 1/2" 10 CM
|  | 0 | 0 | 0 | NIPLE HG 1/2" 15CM
|  | 0 | 0 | 0 | NIPLE HG 1/2" 20 CM
|  | 0 | 0 | 0 | NIPLE HG 1/2" 100 CM
|  | 0 | 0 | 0 | NIPLE HG 1/2 120 CM
|  | 0 | 0 | 0 | NIPLE HG 1/2" 150 CM
|  | 0 | 125 | 0 | TUBO HG 1/2"
|  | 0 | 240 | 0 | VALVULA DE FLOTE 1/2" HELBERT
|  | 0 | 35 | 0 | PICHACHA 2" BRONCE
|  | 0 | SUB-TOTAL | 0
|  | 0 |  | 0 | PVC
|  | 0 | 2.5 | 0 | ADAPTADORA MACHO 1/2"
| 5 | 5 | 36.75 | 183.75 | COPLAS 3"
2 |  | 2 | 44 | 88 | TAPON DE LIMPIEZA 3" CON ROSCA
2 |  | 2 | 44 | 88 | ADAPTADOR HEMBRA 3"
2 | 2 | 4 | 23 | 92 | CURVA PARA DRENAJE 90° 3"
|  | 0 | 14 | 0 | CURVA PARA DRENAJE 90° 2"
2 | 10 | 12 | 18 | 216 | TEE SANITARIO 3"
|  | 0 | 50 | 0 | CRUZ DRENAJE 2"
3 | 3 | 6 | 68 | 408 | TUBO BAJA PLUVIAL- DRENAJE 3"
|  | 0 | 48 | 0 | TUBO BAJA PLUVIAL- DRENAJE 2"
|  | 0 | 190 | 0 | PEGAMENTO 1/4 gal
|  |  | SUB-TOTAL | 1075.75 |  | SEPTIC TANK UNDER BATHROOMS --UNDER CONSTRUCTION
|  |  | TOTAL | 47067.75

## VILLAGE CONTRIBUTION
VILLAGE CONTRIBUTION
1 | WALL STYLE HAND WASHING STATION | MONITARY CONTRIBUTION-$ | WALL STYLE AND 5,500 LITER TANK
| · Three un-skilled laborers working for five days @$8.00 PER MAN DAY | 120 | 543
| · Up to 60 wheelbarrows of rock--1- 5 Cubic meter truck | 53
| · A minimum of two 110 gallon barrels of water per day- 1- pickup | 13
| · Safe and secure storage room for materials. | 0
| Lunch each day for two masons | 26
| Unforseen expenses to adapt to roofs and water lines | 20
| TOTAL | 232 | 543
| C10 Times three----times two | 696 | 464
2 | 2000 LITER HAND WASHING STATION | MONITARY CONTRIBUTION-$
| · Four un-skilled laborers working for ten days | 120
| · Up to 120 wheelbarrows of large rock | 106
| · A minimum of two 110 gallon barrels of water per day- 1- pickup | 13
| · Safe and secure storage room for materials. | 0
| Lunch each day for two masons | 52
| Unforseen expenses to adapt to roofs and water lines | 20
| TOTAL | 311
3 | 5,500 LITER RAIN STORAGE TANK | MONITARY CONTRIBUTION-$
| · Four un-skilled laborers working for 15 days | 120
| · Up to 150 wheelbarrows of large rock | 130
| · A minimum of two 110 gallon barrels of water per day- 1- pickup | 13
| · Safe and secure storage room for materials. | 0
| Lunch each day for two masons | 78
| Unforseen expenses to adapt to roofs and water lines | 20
| TOTAL | 361
4 | SEPTIC TANK | MONITARY CONTRIBUTION-$
| · Four un-skilled laborers working for 15 days | 120
| · Up to 150 wheelbarrows of large rock | 130
| · A minimum of two 110 gallon barrels of water per day- 1- pickup | 13
| · Safe and secure storage room for materials. | 0
| Lunch each day for two masons | 78
| Unforseen expenses to adapt to roofs and water lines | 20
| TOTAL | 361