# Implementation Timeline

Project implementation will begin as soon as funding is received. The following chart indicates the estimated amount of time required for each project task.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Month 1 | Month 2 | Month 3 | Month 4  |
| No. | Activities | Responsible Agency | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 |
| 1 | Investigate, negotiate and evaluate beneficiaries | EMW in coordination with local partners | X |  |  |  |   |   |   |   |   |   |   |   |   |   |   |   |
| 2 | Sign MOU between School and EMW | EMW and local partners |   |  X | X  |   |  |  |   |   |   |   |   |   |   |   |   |   |
|  3 | Organize bidding and bidding evaluation for water treatment system supply and installation | EMW |   |   |   |  X | X  |   |  |  |   |   |   |   |   |   |   |   |
| 4 | Drill one pump well at school | Contractor |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| 5 | Water testing  | Contractor |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| 6 | Conduct Qualitative School Survey and Hygiene Awareness Campaign | EMW and local partners |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |  |
| 7 | Install pipe | Contractor |   |   |   |   |   |  X | X  | X  | X | X |  |  |  |  |   |   |
| 8 | Transport and install water treatment system | Contractor |   |   |   |   |   |   |   |   | X | X | X | X | X | X |   |   |
| 9 | Complete reports for EMW |  Program Manager |   |   |   |   |   |   |   |   |   |   |   |   |   |   | X |   |
| 10 | Send documents and reports to donors | EMW and donors |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   | X |