## Schools in Corail
Report to PWH--Deliveribles
Hygiene Training has been conducted and water filter systems have been installed in the following instititions:
Period from:April 29 to May 9,2010
Coordinator:Seraphin Rony
School ID | Name Of school | Department | Commune | Address | Principal's Name | Principals Phone | (Contract) Been Appriated and taken effect on | Seats | Latitude (Nord) | Longitude (West) | Number of Elev.( Ft) | Filt. Deliv. Lids, Medias | Sanitary buckets qt. deliv./ lids | Sources Buck. qt. deliv./ lids | Filt. Cond. | Filter ID | Installation Status. | Technicians | Postres' Number | Training session in Corail 6→8 May 2010 | Full Name | Phone | Address
Co-0001 | Ecole National Mixte De Corail | Grand'anse | Corail | Corail rue per Benier prolongee | Antoine Gladys | 3637-1242 | 2010-03-05 | 300 | 18'33.966'N | 073'53.571'W | 99 | Yes | 4 | 2 | Good | 03027'03041,03581,03029 | Yes | Del | 00307 |  | Rony Lundor/Jn Fritznel Louis | 3813-1453/3620-1747 | Corail
Co-0002 | Lycee National De Corail | Grand'anse | Corail | Corail rue per Benier prolongee | Henock Papillon | 3659-5618 | 2010-03-05 | 339 | 18'33.966'N | 073'53.571'W | 99 | Yes | 3 | 2 | Good | 03027'03041,03581,03029 | Yes | Del | 00303 |  | Henock Papillon/Jean Riguad | 3659-5618/3612-6473 | Corail
Co-0003 | Ecole St Jean Bosco 1er cycle | Grand'anse | Corail | Centre-ville de Corail,Fond fievreux | Xavier Guillaume | 3793-1605/3773-1801 | 2010-03-05 | 255 | 18'34.020'N | 073'53.347'W | 49 | Yes | 3 | 2 | Good | 03822'03820'03191 | Yes | Del | 00309 |  | Claudel Remy | 3854-5960 | Centre-ville
Co-0004 | Ecole St Jean Bosco 2eme cycle | Grand'anse | Corail | Centre-ville de Corail,Fond fievreux | Xavier Guillaume | 3793-1605/3773-1801 | 2010-03-05 | 351 | 18'34.063'N | 073'53.150'W | 38 | Yes | 4 | 2 | Good | 03049,03239'03519,03726 | Yes | Del | 00280 |  | Xavier Guillaume | 3793-1605 | Centre-ville
Co-0005 | Ecole Mahranatha | Grand'anse | Corail | 4,rue pere Cayemite,Corail | Nelson Josue | 3704-0725/3805-5306 | 2010-03-05 | 374 | 18'34.022'N | 073'53.547'W | -6 | Yes | 4 | 2 | Good | 03582,03573,03052 | Yes | Del | 00305 |  | Leosthene Decade/Josue Nelson | 3805-5306/3704-0725 | Centre-ville
Co-0006 | Institution Evangelique Emmanuel (IEE) | Grand'anse | Corail | 37,rue pere Bernier,corai,Grand'Anse | Joze Honore | 3717-6579/3602-6778 | 2010-03-05 | 112 | 18'34.000N | 073'53.476'W | 63 | Yes | 1 | 1 | Good | 03070 | Yes | Del | 00310 |  | Joze Honore/Kaleb Honore | 3717-6579/3602-6778 | Corail
Co-0007 | Ecole Tipa Tipa | Grand'anse | Corail | Corail | Montchewl Alcegaire | 3863-8072 | 2010-03-05 | 70 | 18'33.990'N | 073'53.811'W | 69 | Yes | 1 | 1 | Good | 03250 | Yes | Del | 00301 |  | Pierre Louis Biesson | 3791-6978 | Corail,ti plaine
Co-0008 | Ecole National Mixte De Champy | Grand'anse | Corail | patte-large.3eme section champy | Marie Ernisse Hory | 3768-2588 | 2010-03-05 | 186 |  |  |  | Yes | 2 | 1 | Good | 03028,03048 | No | _ | 00306 |  | Marie Ernisse Hory/Leonne Fremont | 3768-2588/3812-1288 | Champy 3e section
Co-0009 | Ecole Hirondelle Des Petits | Grand'anse | Corail | Corail | Denis Vivianne | 3634-1131 | 2010-03-05 | 30 | 18'34.041'N | 073'53.367'W | -6 | Yes | 1 | 1 | Good | 03188 | Yes | Del | 00000 |  | Denis Vivianne | 3634-1131 | Centre-ville
Co-0010 | Ecole Communautaire Des Enfants Demunis | Grand'anse | Corail | Corail,Centre-ville | Erick Frataigne | 3830-4329 | 2010-03-05 | 86 | 18'34.061'N | 073'53.437'W | 27 | Yes | 2 | 1 | Good | '03105,03796,03522 | Yes | Del | 00300 |  | Erick Frataigne | 3830-4329 | Centre-ville
Co-0011 | College Des Professeurs Reunis | Grand'anse | Corail | Rue Amiral Killick #110 | Pierre Antoine Louis | 3780-3050 | 2010-03-05 | 100 | 18'34.071'N | 073'53.543'W | 20 | Yes | 1 | 1 | Good | 03077 | Yes | Del | 00304 |  | Ronald Victor/Maxcia Alex | 3737-1980/3716-2295 | Centre-ville
Co-0012 | College Saint Pierre Des Apotres | Grand'anse | Corail | Rue Pere Bernier,a cote l'eglise st pierre apotre | Antonio Jeanite | 3733-1177 | 2010-03-05 | 80 | 18'34.063'N | 073'53.151'W | 32 | Yes | 1 | 1 | Good | 03084 | Yes | Del | 00308 |  | Henock Papillon/Jean Riguad | 3659-5618/3612-6473 | Centre-ville
Co-0013 | College Unions Des Universitaires De Corail (CUUC) | Grand'anse | Corail | 120,rue Dr.Jacques Comelus,Corail | Siffrard Macelot | 3740-7653/3770-6938 | 2010-03-05 | 230 | 18'34.037'N | 073'53.366'w | 6 | Yes | 4 | 2 | Good | 03105,03796,03522 | Yes | Del | 00298 |  | Marcelot Sffrard | 3740-7653 | Centre-ville
Co-0014 | Ecole National De Duquillon | Grand'anse | Corail | Duquillon | Joel Francois | 3759-9703 | 2010-03-05 | 58 | 18'32.045'N | 073'52.133'W | 865 | Yes | 2 | 1 | Good | 03516,03702 | Yes | Del | 00286 |  | Francois Joel | 3759-9703 | Duquillon
Co-0015 | Institution Evangelique Emmanuel de duquillon | Grand'anse | Corail | Duquillon | Joel Bernier | 3643-2280 | 2010-03-05 | 533 | 18'32.401'N | 073'52.541'W | 856 | Yes | 1 | 1 | Good | 035187 | Yes | Del | 00302 |  | Jeol Bernier | 3643-2280 | Duquillon
Co-0016 | Ecole National Fond Ycaque |  | Corail | Fond ycaque 2e section | [16 empty] | Lindor Moralex | 3865-0729 | Fond ycaque

## Homes at Lambi Island
Home ID | Name Of responsible | Department | Commune | Address | Responsible phone | (Contract) Been Appriated and taken effect on | Number of people | Latitude (Nord) | Longitude (West) | Number of Elev.( Ft) | Sanitary buckets qt. deliv./ lids | Sources Buck. qt. deliv./ lids | Filt. Cond. | Installation Status. | Technicians | Training session in Corail 6→8 May 2010 | Full Name | Phone | Address
0001 | Charles | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 3 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee |  | Philip Sejour | 3681-8960 | Lambi Island
0002 | Archibal | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee |  | Neve Sejour | 3687-7723 | Lambi Island
0003 | Riocardo Belle-Garde | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee |  | Dila Merlette | 3842-0492 | Lambi Island
0004 | Fleuriot Roland | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 6 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0005 | Lorguet Alberta | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 6 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0006 | Michel Marianne | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 4 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0007 | Lorguet Alfred | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 6 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0008 | Erline Larguet | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 12 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0009 | Lucnert Merlette | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 14 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0010 | Rezilia Michelle | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 8 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0011 | Queda Louis-Charles | Grand'Anse | Corail | Lambi Island | 3777-3738 | 2010-05-05 | 6 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
00012 | Willy | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 3 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0013 | Lide Elionne | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 4 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0014 | Jn.Claude Belgarde | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 16 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0015 | Manitha | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 10 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0016 | Charles Oliciwa | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 12 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0017 | Anitha Dudieu | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 4 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0018 | Lusianna | Grand'Anse | Corail | Lambi Island | 3681-8960 | 2010-05-05 | 6 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0019 | Venat Charles | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 6 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0020 | Naviala Francois | Grand'Anse | Corail | Lambi Island | 3639-2079 | 2010-05-05 | 2 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0021 | Guivand Pierre-Louis | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 4 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0022 | Wesly Ylaire | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 7 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0023 | Jean Belle-Garde | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 6 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0024 | Denisse Ylaire | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 3 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0025 | Sonon Nerva | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 3 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0026 | Resinal | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 8 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0027 | Vena Diomanche | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 6 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0028 | Benose Sanon | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 9 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0029 | Litha Laguet | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 8 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0030 | Janise Alborfah | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 3 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0031 | Jean Merci-dieu | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 12 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0032 | Pierre-Louis Ojeff | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 2 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0033 | Presly Merllette | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 4 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0034 | Irha Sejour | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 10 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0035 | Ersantha Michelle | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 7 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0036 | Joseph Jean Erole | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 9 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0037 | Erlicien Dimanche | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 3 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0038 | Mervillus Sejour | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0039 | Aurismas Beauvilice | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0040 | Lusia Sejour | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 8 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0041 | Pierre-Louis Sanel | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 4 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0042 | Macli Michel | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 3 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0043 | Odrique Sejour ( Neve ) | Grand'Anse | Corail | Lambi Island | 3687-7723 | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0044 | Anile Pierre | Grand'Anse | Corail | Lambi Island | 3844-047 | 2010-05-05 | 7 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0045 | Merlette Dulia | Grand'Anse | Corail | Lambi Island | 3842-0492 | 2010-05-05 | 2 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0046 | Pajero | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0047 | Ylaire Wener | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 3 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0048 | Charles Elma | Grand'Anse | Corail | Lambi Island | 3789-2945 | 2010-05-05 | 8 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0049 | Sionel Sejour | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 4 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0050 | Merlaile Mirlande | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 4 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0051 | Joseph Orceis | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 7 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0052 | Merlaile Miclau | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 8 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0053 | Jean Ddonese | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 3 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0054 | Jetha Laguet | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 7 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0055 | Jeance Charles | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 6 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0056 | Michel Merlette | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0057 | Toussaint Jean-Cot | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 7 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0058 | Sanon Cabenert | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 9 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0059 | Merlette Pieere Claude | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 3 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0060 | Charles Wima | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0061 | Sejour Clarel | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0062 | Alez Dudieu | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 4 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0063 | Nelio Dimanche | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0064 | Maxen Lageure | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0065 | Ylaire Wesley | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 4 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0066 | Almiste Thomas | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 5 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0067 | Alcide Almas | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 3 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0068 | Sanon renald | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 7 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee
0069 | Evenel Pierre-Louis | Grand'Anse | Corail | Lambi Island | N/A | 2010-05-05 | 4 | 18'37.334'N | 073'50.442'W | 14 | 1 | 1 | Good | Yes | Committee