|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|

|  |  |
| --- | --- |
| **Subject:** | **RE: Details about the school project.** |
| **From:** | **irene kityo <irenekityo2004@yahoo.com>** |
| **Date:** | **Wed, Mar 23, 2011 4:10 am** |
| **To:** | **erinh@appliedphenom.org** |
| **Cc:** | **teddy.n.mwonyonyi@cmsdnet.net** |
| **Attach:** | **sigimg1** |
|  | **icon\_sm\_facebook.gif** |

 |

 |

 |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|

|  |  |  |  |
| --- | --- | --- | --- |
|

|  |  |  |
| --- | --- | --- |
|

|  |  |
| --- | --- |
|

|  |
| --- |
| Hullo Erina,hope all is  fine.Thanks for having the heart of helping schools in developing countries.I really appreciate your effort to have our schools grow.Such development partners like you are really important for our developing education sector. On that,i therefore offer to act as the project manager and site supervisor,which site supervision i will conduct free of charge without payment for i would love to see our country grow.I also took on the initiative to bargain with the contractor to have some costs reduced to the benefit of the school. Since you are also offering charity.I therefore attach the revised budget for the project. As regards your questions,when do you expect the funds to be available? Availability of funds Will be the basis of our planning.This is important because we have to book the contractor earlier because such are not many in Uganda.Mulajje is located 45km away from Kampala and some materials will be transported from Town.We really need to plan a head.The project will take between 4-5 months.About the engineer, am in position to find a competent engineer to help with the technical guidance.You can always anytime you need my help. **Project costs.** I**tems**          **Activity**                       **Amount(Ug shs)**        **Amount($)**1.                   Needs Analysis   .              600,000                       2502.                   Siting and design              2,880,000                      12003.                   Borehole Drilling                24,000,000                   10,0004.                   Transportation                   1444,000                          6005                     Project Manager                6,000,000                      25006.                    Borehole Maintainance       720,000                          3007.                    Site Engineer                     1,440,000                       6008.                    **Total**                               **37,080,000**                  **15,450** **The prices are based on the current dollar rate.** **Regards to all and wish you all the best.** |

 |

 |

 |

 |